## Project tasks
Project name | Petrojam 2.0
Plan owner | Leah Noelte
Project start date | 2025-06-01 23:00
Project finish date | 2027-02-05 17:00
Duration | 440 days
% complete | 5%
Exported on | 2025-06-25 09:59
Task number | Outline number | Color | Name | Update | Finish | % complete | Assigned to | Labels | Depends on | Bucket | Priority | Sprint | Start | Dependents (after) | Effort | Effort completed | Effort remaining | Duration | Milestone | Notes | Completed | Checklist Items | Goal
1 | 1 | Black Outline | Pre-Kick Off Plan |  | 2025-10-08 16:00 | 25% |  |  |  |  | Medium |  | 2025-06-02 08:00 |  | 1784 hours | 488 hours | 1296 hours | 93 days | No
2 | 1.1 | Black | Client Onboarding |  | 2025-07-04 16:00 | 100% |  |  |  |  | Medium |  | 2025-06-02 08:00 |  | 208 hours | 208 hours | 0 hours | 25 days | No
3 | 1.1.1 | Orange | Review Existing Case Studies |  | 2025-06-20 16:00 | 100% | Leah Noelte, Kean Zhu | IES |  | Pre-Kick Off Planning | Medium | Backlog | 2025-06-02 08:00 | 4FS | 48 hours | 48 hours | 0 hours | 15 days | No
4 | 1.1.2 | Orange | List Initial Target Benefit Ideas |  | 2025-07-04 16:00 | 100% | Leah Noelte, Kean Zhu | IES | 3FS | Pre-Kick Off Planning | Medium | Backlog | 2025-06-23 08:00 |  | 160 hours | 160 hours | 0 hours | 10 days | No
5 | 1.2 | Orange | Set Up project On MS Cloud |  | 2025-06-16 16:00 | 100% |  | IES |  | Pre-Kick Off Planning | Medium | Backlog | 2025-06-02 08:00 |  | 8 hours | 8 hours | 0 hours | 11 days | No |  | 4/5 | Save Onboarding documents to SharePoint;Set up Teams Channel;Set up OneNote Sections;Set Up SharePoint Folders;Set Up OneDrive Folders
6 | 1.3 | Black | Develop Scope |  | 2025-09-18 16:00 | 19% |  |  |  |  | Medium |  | 2025-06-02 08:00 | 92FS | 896 hours | 272 hours | 624 hours | 79 days | No
7 | 1.3.1 | Grey | Preparation |  | 2025-06-27 16:00 | 20% |  |  |  |  | Medium |  | 2025-06-02 08:00 |  | 152 hours | 40 hours | 112 hours | 20 days | No
8 | 1.3.1.1 | Orange | Research & Review Client Process |  | 2025-06-27 16:00 | 0% |  | IES;BD;CS |  | Pre-Kick Off Planning | Medium | Backlog | 2025-06-02 08:00 | 10FS, 9FS, 23FS | 112 hours | 0 hours | 112 hours | 20 days | No | Focus research on understanding process, determining benefit categories, determining pain points etc.
9 | 1.3.1.2 | Orange | Determine most viable sites | Only 1 site | 2025-06-26 16:00 | 100% |  | IES;BD;EPA | 8FS | Pre-Kick Off Planning | Medium | Backlog | 2025-06-20 08:00 |  | 40 hours | 40 hours | 0 hours | 5 days | No | Review client estate to determine the most profitable sites and potential for benefit
10 | 1.3.2 | Orange | Determine Use Cases |  | 2025-08-01 16:00 | 0% |  | IES;BD | 8FS | Pre-Kick Off Planning | Medium | Backlog | 2025-07-21 08:00 | 11FS, 17FS, 28FS, 34FS, 12FS, 69FS | 80 hours | 0 hours | 80 hours | 10 days | No | From client research and previous client case studies determine first draft of use cases/benefit categories we will focus on. |  |  | Pre-Kick Off Plan Activities
11 | 1.3.3 | Grey | Profit & Loss (P&L) |  | 2025-08-28 16:00 | 0% |  | IES | 10FS |  | Medium |  | 2025-08-04 08:00 |  | 160 hours | 0 hours | 160 hours | 19 days | No |  | 0/4 | Update for specific sites;Review with Teams;Create P&L;Extract financial info
12 | 1.3.3.1 | Orange | P&L - 1st Draft |  | 2025-08-13 16:00 | 0% |  | IES | 10FS | Pre-Kick Off Planning | Medium | Backlog | 2025-08-04 08:00 | 13FS | 64 hours | 0 hours | 64 hours | 8 days | No | Using skeleton P&L as basis: extract financial information from client (revenue, expenses, income, production). Use the internet, 10-K etc. and use the most recent year. For each use case determine whether that will provide a cost saving (expense scope) or revenue uplift (revenue scope). Determine benefit percentages of the expenses/revenue based on precious clients, industry knowledge, or internet research. | 0/4 | Write out all assumptions for calculation;Determine benefit percentages;Add series and use cases;Extract financial info from 10-K | Pre-Kick Off Plan Activities
13 | 1.3.3.2 | Orange | P&L - Review |  | 2025-08-27 16:00 | 0% |  | CS | 12FS | Pre-Kick Off Planning | Medium | Backlog | 2025-08-14 08:00 | 15FS, 14FS | 80 hours | 0 hours | 80 hours | 10 days | No |  | 0/2 | Recieve CS Sign Off on P&L;Update P&L based on Team Review
14 | 1.3.3.3 | Orange | P&L - Value Optimization Analysis |  | 2025-08-28 16:00 | 0% |  | IES | 13FS | Pre-Kick Off Planning | Medium | Backlog | 2025-08-28 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | Create a one page overview of all the information on the P&L. Total revenues, costs, series separated benefits, revenue benefit, cost savings etc. | 1/1 | Create one page VOA
15 | 1.3.3.4 | Orange | P&L - Finalized |  | 2025-08-28 16:00 | 0% |  | IES | 13FS | Pre-Kick Off Planning | Medium | Backlog | 2025-08-28 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | Update with Matt's Comments | 0/4 | Save Value Optimization Analysis to OneDrive;Update Value Optimization Analysis;Save to OneDrive;Publish to BD | Pre-Kick Off Plan Activities
16 | 1.3.4 | Grey | Statement of Work (SOW) |  | 2025-09-03 16:00 | 56% |  |  |  |  | Medium |  | 2025-08-04 08:00 |  | 312 hours | 224 hours | 88 hours | 23 days | No
17 | 1.3.4.1 | Orange | SOW - 1st Draft |  | 2025-08-21 16:00 | 100% | Leah Noelte, Kean Zhu | IES | 10FS | Pre-Kick Off Planning | Medium | Backlog | 2025-08-04 08:00 | 18FS | 224 hours | 224 hours | 0 hours | 14 days | No |  |  |  | Pre-Kick Off Plan Activities
18 | 1.3.4.2 | Orange | SOW - Review Draft with CS |  | 2025-08-27 16:00 | 0% |  | IES;CS | 17FS | Pre-Kick Off Planning | Medium | Backlog | 2025-08-22 08:00 | 19FS, 20FS, 21FS | 32 hours | 0 hours | 32 hours | 4 days | No
19 | 1.3.4.3 | Orange | SOW - Format & Update Design Elements |  | 2025-08-29 16:00 | 0% |  | Design | 18FS | Pre-Kick Off Planning | Medium | Backlog | 2025-08-28 08:00 | 21FS | 16 hours | 0 hours | 16 hours | 2 days | No
20 | 1.3.4.4 | Orange | SOW - Confirm Indicative IT Architecture |  | 2025-08-29 16:00 | 0% |  | IT | 18FS | Pre-Kick Off Planning | Medium | Backlog | 2025-08-28 08:00 | 40FS, 21FS | 16 hours | 0 hours | 16 hours | 2 days | No
21 | 1.3.4.5 | Orange | SOW - Finalized |  | 2025-09-03 16:00 | 0% |  | IES | 18FS, 19FS, 20FS | Pre-Kick Off Planning | Medium | Backlog | 2025-09-01 08:00 | 24FS, 29FS | 24 hours | 0 hours | 24 hours | 3 days | No |  | 2/2 | Publish to OneDrive;Receive Executive Sign Off
22 | 1.3.5 | Grey | Create DRT |  | 2025-09-10 16:00 | 14% |  |  |  |  | Medium |  | 2025-06-20 08:00 | 54FS | 56 hours | 8 hours | 48 hours | 59 days | No
23 | 1.3.5.1 | Orange | DRT - 1st Draft |  | 2025-06-20 16:00 | 100% | Kean Zhu | IES | 8FS | Pre-Kick Off Planning | Medium | Backlog | 2025-06-20 08:00 | 24FS | 8 hours | 8 hours | 0 hours | 1 day | No | Create 1st Draft of DRT. This will need to be updated after completing SOW. |  |  | Pre-Kick Off Plan Activities
24 | 1.3.5.2 | Orange | DRT - Review |  | 2025-09-08 16:00 | 0% |  | CS | 23FS, 21FS | Pre-Kick Off Planning | Medium | Backlog | 2025-09-04 08:00 | 25FS, 26FS | 24 hours | 0 hours | 24 hours | 3 days | No | After updating wrt SOW review with CS. IES will make any necessary updates | 3/3 | Receive CS go ahead;CS to make any updates;Update wrt SOW
25 | 1.3.5.3 | Orange | Develop Data Source System Roadmap |  | 2025-09-10 16:00 | 0% |  | IES | 24FS | Pre-Kick Off Planning | Medium | Backlog | 2025-09-09 08:00 |  | 16 hours | 0 hours | 16 hours | 2 days | No | Work with LYB to determine LYB specific data source systems with respect to the DRT
26 | 1.3.5.4 | Orange | DRT - Finalized |  | 2025-09-09 16:00 | 0% |  | IES | 24FS | Pre-Kick Off Planning | Medium | Backlog | 2025-09-09 08:00 | 47FS | 8 hours | 0 hours | 8 hours | 1 day | No |  | 1/2 | Save final DRT to OneDrive;Publish DRT to BD | Pre-Kick Off Plan Activities
27 | 1.3.6 | Grey | Executive Presentation (EP) |  | 2025-09-18 16:00 | 0% |  |  |  |  | Medium |  | 2025-08-04 08:00 |  | 136 hours | 0 hours | 136 hours | 34 days | No
28 | 1.3.6.1 | Orange | EP - 1st Draft |  | 2025-08-11 16:00 | 0% |  | IES;CS | 10FS | Pre-Kick Off Planning | Medium | Backlog | 2025-08-04 08:00 | 29FS | 48 hours | 0 hours | 48 hours | 6 days | No |  |  |  | Pre-Kick Off Plan Activities
29 | 1.3.6.2 | Orange | EP - Review Draft with CS |  | 2025-09-10 16:00 | 0% |  | IES;CS | 28FS, 21FS | Pre-Kick Off Planning | Medium | Backlog | 2025-09-04 08:00 | 30FS, 31FS | 40 hours | 0 hours | 40 hours | 5 days | No |  | 0/3 | Receive CS sign off;Review EP with CS;Update EP with any details from SOW
30 | 1.3.6.3 | Orange | EP - Update Design Elements |  | 2025-09-11 16:00 | 0% |  | Design | 29FS | Pre-Kick Off Planning | Medium | Backlog | 2025-09-11 08:00 | 31FS | 8 hours | 0 hours | 8 hours | 1 day | No
31 | 1.3.6.4 | Orange | EP - Final Draft |  | 2025-09-18 16:00 | 0% |  | IES;CS | 30FS, 29FS | Pre-Kick Off Planning | Medium | Backlog | 2025-09-12 08:00 |  | 40 hours | 0 hours | 40 hours | 5 days | No |  | 0/2 | Publish to OneDrive;Receive Executive Sign Off | Pre-Kick Off Plan Activities
32 | 1.4 | Black | Initiate Benefit Measurement Workstream |  | 2025-10-08 16:00 | 0% |  |  |  |  | Medium |  | 2025-08-07 08:00 |  | 336 hours | 0 hours | 336 hours | 45 days | No
33 | 1.4.1 | Orange | Arrange briefing call with EPA |  | 2025-08-07 16:00 | 0% |  | CS;IES;Legal;EPA |  | Pre-Kick Off Planning | Medium | Backlog | 2025-08-07 08:00 | 35FS | 8 hours | 0 hours | 8 hours | 1 day | No
34 | 1.4.2 | Orange | Outline rough case studies |  | 2025-09-10 16:00 | 0% |  | CS;IES | 10FS | Pre-Kick Off Planning | Medium | Backlog | 2025-09-02 08:00 |  | 56 hours | 0 hours | 56 hours | 7 days | No |  | 3/4 | Review;Production Yield;Fuel Balance;Steam Network | Pre-Kick Off Plan Activities
35 | 1.4.3 | Orange | Begin drafting BCMS using previous examples |  | 2025-09-04 16:00 | 0% |  | EPA | 33FS | Pre-Kick Off Planning | Medium | Backlog | 2025-09-02 08:00 | 37FS, 36FS | 24 hours | 0 hours | 24 hours | 3 days | No
36 | 1.4.4 | Orange | Work with Legal team to draft the final BCMs |  | 2025-09-15 16:00 | 0% |  | EPA;Legal;Exec | 35FS | Pre-Kick Off Planning | Medium | Backlog | 2025-09-05 08:00 |  | 56 hours | 0 hours | 56 hours | 7 days | No
37 | 1.4.5 | Orange | Liaise with Legal to Complete Drafts |  | 2025-10-08 16:00 | 0% |  | CS;Legal;Exec | 35FS | Pre-Kick Off Planning | Medium | Backlog | 2025-09-05 08:00 | 79FS | 192 hours | 0 hours | 192 hours | 24 days | No |  |  |  | Pre-Kick Off Plan Activities
38 | 1.5 | Black | IT Architecture Discussion |  | 2025-09-25 16:00 | 0% |  |  |  |  | Medium |  | 2025-07-31 08:00 |  | 144 hours | 0 hours | 144 hours | 41 days | No
39 | 1.5.1 | Orange | Arrange call with Sam Babler, if required |  | 2025-07-31 16:00 | 0% |  | BD;CS;Exec;IES;IT |  | Pre-Kick Off Planning | Medium | Backlog | 2025-07-31 08:00 | 40FS | 8 hours | 0 hours | 8 hours | 1 day | No
40 | 1.5.2 | Orange | Prepare IT Architecture Diagram |  | 2025-09-05 16:00 | 0% |  | BD;CS;IT | 20FS, 39FS | Pre-Kick Off Planning | Medium | Backlog | 2025-09-01 08:00 | 62FS, 372FS, 41FS | 40 hours | 0 hours | 40 hours | 5 days | No | Revise with Specific Systems, Network Segments Used, IP adresses used, Ports and protocols used, Data Flow | 0/1 | Identify IT contact to provide locations & netowrk addressing | Pre-Kick Off Plan Activities
41 | 1.5.3 | Orange | Publish IT Architecture diagram to Client |  | 2025-09-25 16:00 | 0% |  | IT;CS;BD | 40FS | Pre-Kick Off Planning | Medium | Backlog | 2025-09-10 08:00 |  | 96 hours | 0 hours | 96 hours | 12 days | No
42 | 1.6 | Black | External POV and Live Test Preview Call |  | 2025-09-25 16:00 | 0% |  |  |  |  | Medium |  | 2025-09-04 08:00 | 51FS, 55FS, 56FS, 50FS, 52FS | 192 hours | 0 hours | 192 hours | 16 days | No
43 | 1.6.1 | Orange | Submit Security Questionnaire |  | 2025-09-04 16:00 | 0% |  | BD |  | Pre-Kick Off Planning | Medium | Backlog | 2025-09-04 08:00 | 84FS, 44FS | 8 hours | 0 hours | 8 hours | 1 day | No | Submit data security conneciton questionnaire to the client
44 | 1.6.2 | Orange | Security Questionnaire - Client Approval |  | 2025-09-25 16:00 | 0% |  | BD;IT | 43FS | Pre-Kick Off Planning | Medium | Backlog | 2025-09-10 08:00 |  | 96 hours | 0 hours | 96 hours | 12 days | No
45 | 1.6.3 | Orange | Create Kick-Off Planning Presentation |  | 2025-09-23 16:00 | 0% |  | BD;IES |  | Pre-Kick Off Planning | Medium | Backlog | 2025-09-12 08:00 | 47FS, 46FS | 64 hours | 0 hours | 64 hours | 8 days | No |  | 1/4 | Publish to OneDrive;Internal Approval;Design Modifications;Create
46 | 1.6.4 | Orange | Update Kick-Off Presentation Design Elements |  | 2025-09-25 16:00 | 0% |  | Design | 45FS | Pre-Kick Off Planning | Medium | Backlog | 2025-09-24 08:00 |  | 16 hours | 0 hours | 16 hours | 2 days | No
47 | 1.6.5 | Orange | Confirm Kick-Off Meeting Date |  | 2025-09-24 16:00 | 0% |  | BD;CS;Exec | 45FS, 26FS | Pre-Kick Off Planning | Medium | Backlog | 2025-09-24 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No |  | 0/3 | Confirm Client's PM & Exec Sponsor;Set meeting date;Secure correct audience for reveiwing DRT
48 | 2 | Black Outline | POV Kick-Off |  | 2025-12-19 17:00 | 0% |  |  |  |  | Medium |  | 2025-09-24 08:00 |  | 697.6 hours | 0 hours | 697.6 hours | 63 days | No
49 | 2.1 | Black | External Kick-Off Meeting |  | 2025-12-10 17:00 | 0% |  |  |  |  | Medium |  | 2025-10-28 08:00 | 61FS, 84FS | 321.6 hours | 0 hours | 321.6 hours | 32 days | No
50 | 2.1.1 | Orange | Hold External Kick-off Meeting |  | 2025-10-28 16:00 | 0% |  | CS;IES | 42FS | POV Kick-Off | Medium | Backlog | 2025-10-28 08:00 | 59FS, 85FS, 51FS, 52FS, 54FS, 55FS, 56FS, 57FS | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Complete POV
51 | 2.1.2 | Orange | Confirm data sharing method and location |  | 2025-10-29 16:00 | 0% |  | BD;CS;IES | 42FS, 50FS | POV Kick-Off | Medium | Backlog | 2025-10-29 08:00 | 53FS | 8 hours | 0 hours | 8 hours | 1 day | No
52 | 2.1.3 | Orange | Identify server resources |  | 2025-10-29 16:00 | 0% |  | IT | 42FS, 50FS | POV Kick-Off | Medium | Backlog | 2025-10-29 08:00 | 53FS | 8 hours | 0 hours | 8 hours | 1 day | No | Identify any server resources needed
53 | 2.1.4 | Orange | Ensure Elutions equipment is ready |  | 2025-10-30 16:00 | 0% |  | R&D;IT | 51FS, 52FS | POV Kick-Off | Medium | Backlog | 2025-10-30 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | Work with R&D to ensure Elutions’s hosted equipment and infrastructure configuration is ready
54 | 2.1.5 | Orange | Review DRT with client |  | 2025-12-10 17:00 | 0% |  | BD;CS;Exec;IES | 22FS, 50FS | POV Kick-Off | Medium | Backlog | 2025-10-29 08:00 |  | 241.6 hours | 0 hours | 241.6 hours | 31 days | No
55 | 2.1.6 | Orange | Confirm client weekly meeting time |  | 2025-10-29 16:00 | 0% |  | BD;CS;Exec;IES | 42FS, 50FS | POV Kick-Off | Medium | Backlog | 2025-10-29 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No
56 | 2.1.7 | Orange | POV status Update |  | 2025-11-04 17:00 | 0% |  | BD;CS;IES | 42FS, 50FS | POV Kick-Off | Medium | Backlog | 2025-10-29 08:00 |  | 40 hours | 0 hours | 40 hours | 5 days | No |  | 0/3 | Set up ongoing POV Status Update Template;Publish 1st POV status Update;Review POV Status Update
57 | 2.1.8 | Orange | Maestro Demo for wider project team (Optional) |  | 2025-10-29 16:00 | 0% |  | BD;CS;Exec;IES | 50FS | POV Kick-Off | Medium | Backlog | 2025-10-29 08:00 |  |  |  |  | 1 day | No
58 | 2.2 | Black | Kick-Off Call Internal Washup |  | 2025-10-30 16:00 | 0% |  |  |  |  | Medium |  | 2025-10-29 08:00 | 72FS | 16 hours | 0 hours | 16 hours | 2 days | No
59 | 2.2.1 | Orange | Review Meeting Actions with Elutions team |  | 2025-10-29 16:00 | 0% |  | CS | 50FS | POV Kick-Off | Medium | Backlog | 2025-10-29 08:00 | 60FS | 8 hours | 0 hours | 8 hours | 1 day | No
60 | 2.2.2 | Orange | Schedule placeholder for internal weekly calls |  | 2025-10-30 16:00 | 0% |  | CS | 59FS | POV Kick-Off | Medium | Backlog | 2025-10-30 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No
61 | 2.3 | Black | Client Workstream Owner Introductions |  | 2025-12-19 17:00 | 0% |  |  | 49FS |  | Medium |  | 2025-12-11 09:00 |  | 112 hours | 0 hours | 112 hours | 7 days | No
62 | 2.3.1 | Orange | Introductions to client systems and IT resource |  | 2025-12-17 17:00 | 0% |  | CS;SCIE | 40FS | POV Kick-Off | Medium | Backlog | 2025-12-11 09:00 | 63FS, 65FS | 40 hours | 0 hours | 40 hours | 5 days | No
63 | 2.3.2 | Orange | Send Integration Questionaire to Client |  | 2025-12-18 17:00 | 0% |  | SCIE | 62FS | POV Kick-Off | Medium | Backlog | 2025-12-18 09:00 | 64FS | 8 hours | 0 hours | 8 hours | 1 day | No
64 | 2.3.3 | Orange | Receive and Review Integration Questionaire |  | 2025-12-19 17:00 | 0% |  | SCIE | 63FS | POV Kick-Off | Medium | Backlog | 2025-12-19 09:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No
65 | 2.3.4 | Orange | Request VPN Connection |  | 2025-12-18 17:00 | 0% |  | SCIE;IT | 62FS | POV Kick-Off | Medium | Backlog | 2025-12-18 09:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No
66 | 2.3.5 | Orange | Save contract details to OneNote |  | 2025-12-11 17:00 | 0% |  | CS |  | POV Kick-Off | Medium | Backlog | 2025-12-11 09:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No
67 | 2.3.6 | Orange | Introductions to client owners for each workstream |  | 2025-12-17 17:00 | 0% |  | CS |  | POV Kick-Off | Medium | Backlog | 2025-12-11 09:00 |  | 40 hours | 0 hours | 40 hours | 5 days | No
68 | 2.4 | Black | Data Science Preparation |  | 2025-09-26 16:00 | 0% |  |  |  |  | Medium |  | 2025-09-25 08:00 |  | 16 hours | 0 hours | 16 hours | 2 days | No
69 | 2.4.1 | Orange | KT w/ DS for use cases | Meeting scheduled for 4/30 | 2025-09-25 16:00 | 0% |  | IES | 10FS | POV Kick-Off | Medium | Backlog | 2025-09-25 08:00 | 70FS | 8 hours | 0 hours | 8 hours | 1 day | No |  | 2/5 | KT for production yield;KT for Fuel Use Case;KT for Steam Use Case;Set meeting;Prepare similar examples
70 | 2.4.2 | Orange | Familiarize & Practice Modeling |  | 2025-09-26 16:00 | 0% |  | DS | 69FS | POV Kick-Off | Medium | Backlog | 2025-09-26 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | Using previous client data practice modeling client use case KPIs for new use case ideas familiarize with the process and come up with modeling ideas. Streamline modeling selection - which model will be used for each use case. Conditioning data etc.
71 | 2.5 | Black | POV Governance |  | 2025-11-04 17:00 | 0% |  |  |  |  | Medium |  | 2025-09-24 08:00 |  | 232 hours | 0 hours | 232 hours | 30 days | No
72 | 2.5.1 | Grey | Internal Weekly Call |  | 2025-10-31 16:00 | 0% |  |  | 58FS |  | Medium |  | 2025-10-31 08:00 | 75FS | 16 hours | 0 hours | 16 hours | 1 day | No |  | 0/6 | Decide whether to email feedback pior to call;Publish clarificaitions on Teams, internally;Notify team of incoming data;Review data/query;Review clarifications;Set internal weekly call
73 | 2.5.1.1 | Orange | Publish Agenda |  | 2025-10-31 16:00 | 0% |  | IES;CS;BD |  | POV Kick-Off | Medium | Backlog | 2025-10-31 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No
74 | 2.5.1.2 | Orange | Confirm Attendees |  | 2025-10-31 16:00 | 0% |  | CS;BD;IES;Exec |  | POV Kick-Off | Medium | Backlog | 2025-10-31 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No
75 | 2.5.2 | Grey | Weekly Client Call |  | 2025-11-04 17:00 | 0% |  |  | 72FS |  | Medium |  | 2025-11-03 09:00 |  | 16 hours | 0 hours | 16 hours | 2 days | No
76 | 2.5.2.1 | Orange | Publish Weekly Client Call Agenda |  | 2025-11-03 17:00 | 0% |  | BD;CS;Exec |  | POV Kick-Off | Medium | Backlog | 2025-11-03 09:00 | 77FS | 8 hours | 0 hours | 8 hours | 1 day | No |  | 0/2 | Review clarifications;Ensure ccorrect audience for call
77 | 2.5.2.2 | Orange | Confirm Weekly Client Call Attendees |  | 2025-11-04 17:00 | 0% |  | IES;CS;BD;Exec | 76FS | POV Kick-Off | Medium | Backlog | 2025-11-04 09:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No |  | 0/4 | Review actions in POV status update;Update previous week's action tracker & DRT status;Post call notes to OneNote;Attend Call
78 | 2.5.3 | Grey | Contractual Obligations |  | 2025-10-09 16:00 | 0% |  |  |  |  | Medium |  | 2025-09-25 08:00 |  | 96 hours | 0 hours | 96 hours | 11 days | No
79 | 2.5.3.1 | Orange | Share Contractual Obligations |  | 2025-10-09 16:00 | 0% |  | CS | 37FS | POV Kick-Off | Medium | Backlog | 2025-10-09 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No |  | 0/3 | Ensure all key contractual obligations are in OneNote;Confirm key obligations with legal;Share relevent key obligations with the project team
80 | 2.5.3.2 | Orange | Establish processes for ongoing contractual obligations |  | 2025-10-09 16:00 | 0% |  | CS;Legal |  | POV Kick-Off | Medium | Backlog | 2025-09-25 08:00 |  | 88 hours | 0 hours | 88 hours | 11 days | No | How and when to raise shared savings invoices, extensions, etc.
81 | 2.5.4 | Grey | Establish Exec Review Framework |  | 2025-10-10 16:00 | 0% |  |  |  |  | Medium |  | 2025-09-24 08:00 |  | 104 hours | 0 hours | 104 hours | 13 days | No | Publish day after weekly call
82 | 2.5.4.1 | Orange | Create Planner Goals? |  | 2025-10-10 16:00 | 0% |  | CS |  | POV Kick-Off | Medium | Backlog | 2025-09-24 08:00 |  | 104 hours | 0 hours | 104 hours | 13 days | No
83 | 3 | Black Outline | Data Collection & Benefit Measurement |  | 2026-01-09 17:00 | 0% |  |  |  |  | Medium |  | 2025-12-11 09:00 |  | 192 hours | 0 hours | 192 hours | 22 days | No
84 | 3.1 | Black | Historical Data Collection |  | 2026-01-09 17:00 | 0% |  |  | 49FS, 43FS |  | Medium |  | 2025-12-11 09:00 | 111FS, 283FS, 197FS | 192 hours | 0 hours | 192 hours | 22 days | No
85 | 3.1.1 | Orange | Data Collection |  | 2026-01-01 17:00 | 0% |  | IT;SCIE | 50FS | Data Collection & Benefit Measurement | Medium | Backlog | 2025-12-11 09:00 | 86FS | 128 hours | 0 hours | 128 hours | 16 days | No
86 | 3.1.2 | Orange | Complete historical data collection |  | 2026-01-02 17:00 | 0% |  | SCIE;IT | 85FS | Data Collection & Benefit Measurement | Medium | Backlog | 2026-01-02 09:00 | 101FS, 113FS, 87FS, 123FS, 118FS | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Complete POV
87 | 3.1.3 | Orange | Review of historical data |  | 2026-01-05 17:00 | 0% |  | SCIE | 86FS | Data Collection & Benefit Measurement | Medium | Backlog | 2026-01-05 09:00 | 88FS, 89FS, 90FS | 8 hours | 0 hours | 8 hours | 1 day | No | Ensure data is in correct format or convert to necessary format
88 | 3.1.4 | Orange | Creating scripts for historical data transfer |  | 2026-01-09 17:00 | 0% |  | SCIE | 87FS | Data Collection & Benefit Measurement | Medium | Backlog | 2026-01-06 09:00 |  | 32 hours | 0 hours | 32 hours | 4 days | No
89 | 3.1.5 | Orange | Store data in OneDrive |  | 2026-01-06 17:00 | 0% |  | IES | 87FS | Data Collection & Benefit Measurement | Medium | Backlog | 2026-01-06 09:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No |  | 0/2 | Notify team;Store historical data in OneDrive
90 | 3.1.6 | Orange | Update DRT with receipt of data |  | 2026-01-06 17:00 | 0% |  | IES | 87FS | Data Collection & Benefit Measurement | Medium | Backlog | 2026-01-06 09:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No
91 | 4 | Black Outline | Portal Development |  | 2026-01-05 17:00 | 0% |  |  |  |  | Medium |  | 2025-06-02 08:00 |  | 832 hours | 0 hours | 832 hours | 156 days | No
92 | 4.1 | Black | Maestro Screen Design Document |  | 2025-10-15 16:00 | 0% |  |  | 6FS |  | Medium |  | 2025-09-19 08:00 | 102FS, 103FS, 105FS, 107FS | 304 hours | 0 hours | 304 hours | 19 days | No
93 | 4.1.1 | Orange | Outline changes for existing Maestro screens |  | 2025-09-23 16:00 | 0% |  | CS;IES |  | Portal Development | Medium | Backlog | 2025-09-19 08:00 | 94FS | 24 hours | 0 hours | 24 hours | 3 days | No | For each existing screen (where changes are required) take a screenshot of the screen and add the necessary changes.
94 | 4.1.2 | Orange | Create mock ups for existing screens |  | 2025-10-07 16:00 | 0% |  | Design;IES | 93FS | Portal Development | Medium | Backlog | 2025-09-24 08:00 | 95FS | 80 hours | 0 hours | 80 hours | 10 days | No | Create mock-ups within the design document | 2/2 | Internal IES Mockup Modifications;Internal IES Mockup Review
95 | 4.1.3 | Orange | Mock up approval |  | 2025-10-08 16:00 | 0% |  | BD;CS;Exec | 94FS | Portal Development | Medium | Backlog | 2025-10-08 08:00 | 96FS | 8 hours | 0 hours | 8 hours | 1 day | No | Receive approval for newly developed mock ups
96 | 4.1.4 | Orange | Share Mock Ups to R&D |  | 2025-10-09 16:00 | 0% |  | IES | 95FS | Portal Development | Medium | Backlog | 2025-10-09 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | Share mock ups and discuss new additions and changes
97 | 4.1.5 | Orange | Outline where object trees are required |  | 2025-10-15 16:00 | 0% |  | R&D |  | Portal Development | Medium | Backlog | 2025-09-26 08:00 | 106FS | 112 hours | 0 hours | 112 hours | 14 days | No
98 | 4.1.6 | Orange | Provide import files where possible |  | 2025-10-01 16:00 | 0% |  | R&D |  | Portal Development | Medium | Backlog | 2025-09-19 08:00 | 100FS | 72 hours | 0 hours | 72 hours | 9 days | No |  | 0/1 | Need additional information, Not sure what is meant by 'import files'
99 | 4.2 | Black | Develop POV Portal |  | 2026-01-05 17:00 | 0% |  |  |  |  | Medium |  | 2025-06-02 08:00 |  | 528 hours | 0 hours | 528 hours | 156 days | No
100 | 4.2.1 | Orange | IES Import POV Info |  | 2025-10-13 16:00 | 0% |  | IES | 98FS | Portal Development | Medium | Backlog | 2025-10-02 08:00 |  | 64 hours | 0 hours | 64 hours | 8 days | No | Import Case Studies using Maestro import files
101 | 4.2.2 | Orange | DS Import POV info |  | 2026-01-05 17:00 | 0% |  | DS | 86FS | Portal Development | Medium | Backlog | 2026-01-05 09:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | Include correlation tables & anomaly report | 0/2 | anomaly report;Correlation tables
102 | 4.2.3 | Orange | Develop new additional dashboards |  | 2025-10-29 16:00 | 0% |  | R&D | 92FS | Portal Development | Medium | Backlog | 2025-10-16 08:00 | 108FS, 109FS | 80 hours | 0 hours | 80 hours | 10 days | No
103 | 4.2.4 | Orange | Develop process centre |  | 2025-11-04 17:00 | 0% |  | R&D | 92FS | Portal Development | Medium | Backlog | 2025-10-16 08:00 | 109FS | 112 hours | 0 hours | 112 hours | 14 days | No
104 | 4.2.5 | Orange | Create trend viewer |  | 2025-06-03 16:00 | 0% |  | R&D |  | Portal Development | Medium | Backlog | 2025-06-02 08:00 | 109FS | 16 hours | 0 hours | 16 hours | 2 days | No
105 | 4.2.6 | Orange | Develop benefit centre |  | 2025-11-04 17:00 | 0% |  | R&D | 92FS | Portal Development | Medium | Backlog | 2025-10-16 08:00 | 109FS | 112 hours | 0 hours | 112 hours | 14 days | No
106 | 4.2.7 | Orange | Create object tree(s) |  | 2025-10-16 16:00 | 0% |  | R&D | 97FS | Portal Development | Medium | Backlog | 2025-10-16 08:00 | 109FS | 8 hours | 0 hours | 8 hours | 1 day | No
107 | 4.2.8 | Orange | Develop impact centre |  | 2025-11-04 17:00 | 0% |  | R&D | 92FS | Portal Development | Medium | Backlog | 2025-10-16 08:00 | 109FS | 112 hours | 0 hours | 112 hours | 14 days | No
108 | 4.2.9 | Orange | Review existing dashboards for vertical |  | 2025-10-30 16:00 | 0% |  | CS;IES;R&D | 102FS | Portal Development | Medium | Backlog | 2025-10-30 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No
109 | 4.2.10 | Orange | Complete development of POV portal |  | 2025-11-05 17:00 | 0% |  | IES;R&D;BD;CS | 107FS, 106FS, 105FS, 104FS, 103FS, 102FS | Portal Development | Medium | Backlog | 2025-11-05 09:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Complete POV
110 | 5 | Black Outline | Series 1 IBA Development |  | 2026-03-24 16:00 | 0% |  |  |  |  | Medium |  | 2026-01-12 09:00 | 196FS | 1376 hours | 0 hours | 1376 hours | 52 days | No
111 | 5.1 | Black | Data Qualification |  | 2026-01-19 17:00 | 0% |  |  | 84FS |  | Medium |  | 2026-01-12 09:00 |  | 144 hours | 0 hours | 144 hours | 6 days | No
112 | 5.1.1 | Grey | Steam Network Data Qualification |  | 2026-01-19 17:00 | 0% |  |  |  |  | Medium |  | 2026-01-12 09:00 | 129FS | 48 hours | 0 hours | 48 hours | 6 days | No
113 | 5.1.1.1 | Orange | Steam Network - Establish Data Connection |  | 2026-01-12 17:00 | 0% |  | IES;R&D;DS | 86FS | Series 1 IBA Development | Medium | Backlog | 2026-01-12 09:00 | 114FS | 8 hours | 0 hours | 8 hours | 1 day | No | Establish data connection to SQL database and server | 0/2 | R&D grants permissions to necessary members;Send list of DS/IES members that need permissions to R&D
114 | 5.1.1.2 | Orange | Steam Network - Validate Data |  | 2026-01-13 17:00 | 0% |  | IES;R&D | 113FS | Series 1 IBA Development | Medium | Backlog | 2026-01-13 09:00 | 115FS | 8 hours | 0 hours | 8 hours | 1 day | No | Use the DRT to determine the list of data requirements for series 1. | 0/2 | Agree the official receipt of data required to launch;Determine the list of data requirements
115 | 5.1.1.3 | Orange | Steam Network - Check Data Availability |  | 2026-01-16 17:00 | 0% |  | DS | 114FS | Series 1 IBA Development | Medium | Backlog | 2026-01-14 09:00 | 116FS | 24 hours | 0 hours | 24 hours | 3 days | No | Run analysis to check for data availability per tag and per time stamp | 0/2 | Check data health;Check data availability
116 | 5.1.1.4 | Orange | Steam Network - Mark Receipt of Each Data Source |  | 2026-01-19 17:00 | 0% |  | IES | 115FS | Series 1 IBA Development | Medium | Backlog | 2026-01-19 09:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | On receipt of data, mark recept against each previously afreed data source for the benefit idea
117 | 5.1.2 | Grey | Fuel Balance Data Qualification |  | 2026-01-19 17:00 | 0% |  |  |  |  | Medium |  | 2026-01-12 09:00 | 129FS, 136FS | 48 hours | 0 hours | 48 hours | 6 days | No
118 | 5.1.2.1 | Orange | Fuel - Establish Data Connection |  | 2026-01-12 17:00 | 0% |  | IES;R&D;DS | 86FS | Series 1 IBA Development | Medium | Backlog | 2026-01-12 09:00 | 119FS | 8 hours | 0 hours | 8 hours | 1 day | No | Establish data connection to SQL database and server | 0/2 | R&D grants permissions to necessary members;Send list of DS/IES members that need permissions to R&D
119 | 5.1.2.2 | Orange | Fuel - Validate Data |  | 2026-01-13 17:00 | 0% |  | IES;R&D | 118FS | Series 1 IBA Development | Medium | Backlog | 2026-01-13 09:00 | 120FS | 8 hours | 0 hours | 8 hours | 1 day | No | Use the DRT to determine the list of data requirements for series 1. | 0/2 | Agree the official receipt of data required to launch;Determine the list of data requirements
120 | 5.1.2.3 | Orange | Fuel - Check Data Availability |  | 2026-01-16 17:00 | 0% |  | DS | 119FS | Series 1 IBA Development | Medium | Backlog | 2026-01-14 09:00 | 121FS | 24 hours | 0 hours | 24 hours | 3 days | No | Run analysis to check for data availability per tag and per time stamp | 0/2 | Check data health;Check data availability
121 | 5.1.2.4 | Orange | Fuel - Mark Receipt of Each Data Source |  | 2026-01-19 17:00 | 0% |  | IES | 120FS | Series 1 IBA Development | Medium | Backlog | 2026-01-19 09:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | On receipt of data, mark recept against each previously afreed data source for the benefit idea
122 | 5.1.3 | Grey | Production Yield Data Qualification |  | 2026-01-19 17:00 | 0% |  |  |  |  | Medium |  | 2026-01-12 09:00 | 129FS, 143FS | 48 hours | 0 hours | 48 hours | 6 days | No
123 | 5.1.3.1 | Orange | Yield - Establish Data Connection |  | 2026-01-12 17:00 | 0% |  | IES;R&D;DS | 86FS | Series 1 IBA Development | Medium | Backlog | 2026-01-12 09:00 | 124FS | 8 hours | 0 hours | 8 hours | 1 day | No | Establish data connection to SQL database and server | 0/2 | R&D grants permissions to necessary members;Send list of DS/IES members that need permissions to R&D
124 | 5.1.3.2 | Orange | Yield - Validate Data |  | 2026-01-13 17:00 | 0% |  | IES;R&D | 123FS | Series 1 IBA Development | Medium | Backlog | 2026-01-13 09:00 | 125FS | 8 hours | 0 hours | 8 hours | 1 day | No | Use the DRT to determine the list of data requirements for series 1. | 0/2 | Agree the official receipt of data required to launch;Determine the list of data requirements
125 | 5.1.3.3 | Orange | Yield - Check Data Availability |  | 2026-01-16 17:00 | 0% |  | DS | 124FS | Series 1 IBA Development | Medium | Backlog | 2026-01-14 09:00 | 126FS | 24 hours | 0 hours | 24 hours | 3 days | No | Run analysis to check for data availability per tag and per time stamp | 0/2 | Check data health;Check data availability
126 | 5.1.3.4 | Orange | Yield - Mark Receipt of Each Data Source |  | 2026-01-19 17:00 | 0% |  | IES | 125FS | Series 1 IBA Development | Medium | Backlog | 2026-01-19 09:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | On receipt of data, mark recept against each previously afreed data source for the benefit idea
127 | 5.2 | Black | Digital Twin, Mapping and Prediction |  | 2026-02-04 17:00 | 0% |  |  |  |  | Medium |  | 2026-01-20 09:00 |  | 296 hours | 0 hours | 296 hours | 12 days | No
128 | 5.2.1 | Grey | Steam Network Digital Twin |  | 2026-02-03 17:00 | 0% |  |  |  |  | Medium |  | 2026-01-20 09:00 | 149FS | 96 hours | 0 hours | 96 hours | 11 days | No
129 | 5.2.1.1 | Orange | Steam - Determine relevant tags & target |  | 2026-01-22 17:00 | 0% |  | IES | 112FS, 122FS, 117FS | Series 1 IBA Development | Medium | Backlog | 2026-01-20 09:00 | 130FS, 131FS | 24 hours | 0 hours | 24 hours | 3 days | No | For each major unit find all relevant tags for DS to use in a correlation analysis | 0/2 | Provide target KPIs;Determine relevant tags for model
130 | 5.2.1.2 | Orange | Steam - DS KT session |  | 2026-01-23 17:00 | 0% |  | IES | 129FS | Series 1 IBA Development | Medium | Backlog | 2026-01-23 09:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | Sign off the data science KT session where optimization objectives are known | 0/2 | Have DS KT session;Create DS KT documents
131 | 5.2.1.3 | Orange | Steam - Label tags for the models |  | 2026-01-27 17:00 | 0% |  | IES;DS | 129FS | Series 1 IBA Development | Medium | Backlog | 2026-01-23 09:00 | 132FS | 24 hours | 0 hours | 24 hours | 3 days | No | Use process documentation to list control. manipulated, disturbance & constraint tags for each unit. Where possible have DS complete automated list
132 | 5.2.1.4 | Orange | Steam - Create Bounds & Changing Rates |  | 2026-01-28 17:00 | 0% |  | IES;DS | 131FS | Series 1 IBA Development | Medium | Backlog | 2026-01-28 09:00 | 133FS | 8 hours | 0 hours | 8 hours | 1 day | No | IES or DS task. IES would manually look at historical data or DS could create script to determine bounds and changing rates. | 0/3 | Validate based on process knowledge;Create changing rates;Create bounds
133 | 5.2.1.5 | Orange | Steam - Generate model |  | 2026-01-29 17:00 | 0% |  | DS | 132FS | Series 1 IBA Development | Medium | Backlog | 2026-01-29 09:00 | 134FS, 152FS | 8 hours | 0 hours | 8 hours | 1 day | No |  | 0/4 | Get the validation supporting by referring the historical data;Get the model accrucary and confirm with IES team;Get historical optimized directives;Create a model for predicting the target
134 | 5.2.1.6 | Orange | Steam - Ensure correct formatting and that data is uploaded to Maestro |  | 2026-02-03 17:00 | 0% |  | IES;R&D | 133FS | Series 1 IBA Development | Medium | Backlog | 2026-01-30 09:00 |  | 24 hours | 0 hours | 24 hours | 3 days | No
135 | 5.2.2 | Grey | Fuel Balance Digital Twin |  | 2026-02-03 17:00 | 0% |  |  |  |  | Medium |  | 2026-01-20 09:00 | 149FS | 96 hours | 0 hours | 96 hours | 11 days | No
136 | 5.2.2.1 | Orange | Fuel - Determine relevant tags & target |  | 2026-01-22 17:00 | 0% |  | IES | 117FS | Series 1 IBA Development | Medium | Backlog | 2026-01-20 09:00 | 137FS, 138FS | 24 hours | 0 hours | 24 hours | 3 days | No | For each major unit find all relevant tags for DS to use in a correlation analysis | 0/2 | Provide target KPIs;Determine relevant tags for model
137 | 5.2.2.2 | Orange | Fuel - DS KT session |  | 2026-01-23 17:00 | 0% |  | IES | 136FS | Series 1 IBA Development | Medium | Backlog | 2026-01-23 09:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | Sign off the data science KT session where optimization objectives are known | 0/2 | Have DS KT session;Create DS KT documents
138 | 5.2.2.3 | Orange | Fuel - Label tags for the models |  | 2026-01-27 17:00 | 0% |  | IES;DS | 136FS | Series 1 IBA Development | Medium | Backlog | 2026-01-23 09:00 | 139FS | 24 hours | 0 hours | 24 hours | 3 days | No | Use process documentation to list control. manipulated, disturbance & constraint tags for each unit. Where possible have DS complete automated list
139 | 5.2.2.4 | Orange | Fuel - Create Bounds & Changing Rates |  | 2026-01-28 17:00 | 0% |  | IES;DS | 138FS | Series 1 IBA Development | Medium | Backlog | 2026-01-28 09:00 | 140FS | 8 hours | 0 hours | 8 hours | 1 day | No | IES or DS task. IES would manually look at historical data or DS could create script to determine bounds and changing rates. | 0/3 | Validate based on process knowledge;Create changing rates;Create bounds
140 | 5.2.2.5 | Orange | Fuel - Generate model |  | 2026-01-29 17:00 | 0% |  | DS | 139FS | Series 1 IBA Development | Medium | Backlog | 2026-01-29 09:00 | 141FS, 156FS | 8 hours | 0 hours | 8 hours | 1 day | No |  | 0/4 | Get the validation supporting by referring the historical data;Get the model accrucary and confirm with IES team;Get historical optimized directives;Create a model for predicting the target
141 | 5.2.2.6 | Orange | Fuel - Ensure correct formatting and that data is uploaded to Maestro |  | 2026-02-03 17:00 | 0% |  | IES;R&D | 140FS | Series 1 IBA Development | Medium | Backlog | 2026-01-30 09:00 |  | 24 hours | 0 hours | 24 hours | 3 days | No
142 | 5.2.3 | Grey | Production Yield Digital Twin |  | 2026-02-03 17:00 | 0% |  |  |  |  | Medium |  | 2026-01-20 09:00 | 149FS | 96 hours | 0 hours | 96 hours | 11 days | No
143 | 5.2.3.1 | Orange | Yield - Determine relevant tags & target |  | 2026-01-22 17:00 | 0% |  | IES | 122FS | Series 1 IBA Development | Medium | Backlog | 2026-01-20 09:00 | 144FS, 145FS | 24 hours | 0 hours | 24 hours | 3 days | No | For each major unit find all relevant tags for DS to use in a correlation analysis | 0/2 | Provide target KPIs;Determine relevant tags for model
144 | 5.2.3.2 | Orange | Yield - DS KT session |  | 2026-01-23 17:00 | 0% |  | IES | 143FS | Series 1 IBA Development | Medium | Backlog | 2026-01-23 09:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | Sign off the data science KT session where optimization objectives are known | 0/2 | Have DS KT session;Create DS KT documents
145 | 5.2.3.3 | Orange | Yield - Label tags for the models |  | 2026-01-27 17:00 | 0% |  | IES;DS | 143FS | Series 1 IBA Development | Medium | Backlog | 2026-01-23 09:00 | 146FS | 24 hours | 0 hours | 24 hours | 3 days | No | Use process documentation to list control. manipulated, disturbance & constraint tags for each unit. Where possible have DS complete automated list
146 | 5.2.3.4 | Orange | Yield - Create Bounds & Changing Rates |  | 2026-01-28 17:00 | 0% |  | IES;DS | 145FS | Series 1 IBA Development | Medium | Backlog | 2026-01-28 09:00 | 147FS | 8 hours | 0 hours | 8 hours | 1 day | No | IES or DS task. IES would manually look at historical data or DS could create script to determine bounds and changing rates. | 0/3 | Validate based on process knowledge;Create changing rates;Create bounds
147 | 5.2.3.5 | Orange | Yield - Generate model |  | 2026-01-29 17:00 | 0% |  | DS | 146FS | Series 1 IBA Development | Medium | Backlog | 2026-01-29 09:00 | 148FS, 160FS | 8 hours | 0 hours | 8 hours | 1 day | No |  | 0/4 | Get the validation supporting by referring the historical data;Get the model accrucary and confirm with IES team;Get historical optimized directives;Create a model for predicting the target
148 | 5.2.3.6 | Orange | Yield - Ensure correct formatting and that data is uploaded to Maestro |  | 2026-02-03 17:00 | 0% |  | IES;R&D | 147FS | Series 1 IBA Development | Medium | Backlog | 2026-01-30 09:00 |  | 24 hours | 0 hours | 24 hours | 3 days | No
149 | 5.2.4 | Orange | Stack Series Models |  | 2026-02-04 17:00 | 0% |  | DS | 128FS, 142FS, 135FS | Series 1 IBA Development | Medium | Backlog | 2026-02-04 09:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | Stack the models for all the use cases (skeleton only shows a single use case - Steam Network)
150 | 5.3 | Black | Benefit Quantification |  | 2026-02-11 17:00 | 0% |  |  |  |  | Medium |  | 2026-01-30 09:00 |  | 216 hours | 0 hours | 216 hours | 9 days | No
151 | 5.3.1 | Grey | Steam Network Benefit Quantification |  | 2026-02-11 17:00 | 0% |  |  |  |  | Medium |  | 2026-01-30 09:00 | 165FS | 72 hours | 0 hours | 72 hours | 9 days | No
152 | 5.3.1.1 | Orange | Steam - Establish benefit measurement methodology |  | 2026-02-03 17:00 | 0% |  | IES | 133FS | Series 1 IBA Development | Medium | Backlog | 2026-01-30 09:00 | 153FS | 24 hours | 0 hours | 24 hours | 3 days | No
153 | 5.3.1.2 | Orange | Steam - Consult with EPA to learn implementation |  | 2026-02-04 17:00 | 0% |  | EPA;Exec;IES | 152FS | Series 1 IBA Development | Medium | Backlog | 2026-02-04 09:00 | 154FS | 8 hours | 0 hours | 8 hours | 1 day | No | Once benefit is established, consult with EPA for method to learn implementation
154 | 5.3.1.3 | Orange | Steam - Create implementation framework |  | 2026-02-11 17:00 | 0% |  | EPA | 153FS | Series 1 IBA Development | Medium | Backlog | 2026-02-05 09:00 |  | 40 hours | 0 hours | 40 hours | 5 days | No | Create an implementation framwork that allows us to detect implementation (where possible)
155 | 5.3.2 | Grey | Fuel Balance Benefit Quantification |  | 2026-02-11 17:00 | 0% |  |  |  |  | Medium |  | 2026-01-30 09:00 | 169FS | 72 hours | 0 hours | 72 hours | 9 days | No
156 | 5.3.2.1 | Orange | Fuel - Establish benefit measurement methodology |  | 2026-02-03 17:00 | 0% |  | IES | 140FS | Series 1 IBA Development | Medium | Backlog | 2026-01-30 09:00 | 157FS | 24 hours | 0 hours | 24 hours | 3 days | No
157 | 5.3.2.2 | Orange | Fuel - Consult with EPA to learn implementation |  | 2026-02-04 17:00 | 0% |  | EPA;Exec;IES | 156FS | Series 1 IBA Development | Medium | Backlog | 2026-02-04 09:00 | 158FS | 8 hours | 0 hours | 8 hours | 1 day | No | Once benefit is established, consult with EPA for method to learn implementation
158 | 5.3.2.3 | Orange | Fuel - Create implementation framework |  | 2026-02-11 17:00 | 0% |  | EPA | 157FS | Series 1 IBA Development | Medium | Backlog | 2026-02-05 09:00 |  | 40 hours | 0 hours | 40 hours | 5 days | No | Create an implementation framwork that allows us to detect implementation (where possible)
159 | 5.3.3 | Grey | Production Yield Benefit Quantification |  | 2026-02-11 17:00 | 0% |  |  |  |  | Medium |  | 2026-01-30 09:00 | 173FS | 72 hours | 0 hours | 72 hours | 9 days | No
160 | 5.3.3.1 | Orange | Yield - Establish benefit measurement methodology |  | 2026-02-03 17:00 | 0% |  | IES | 147FS | Series 1 IBA Development | Medium | Backlog | 2026-01-30 09:00 | 161FS | 24 hours | 0 hours | 24 hours | 3 days | No
161 | 5.3.3.2 | Orange | Yield - Consult with EPA to learn implementation |  | 2026-02-04 17:00 | 0% |  | EPA;Exec;IES | 160FS | Series 1 IBA Development | Medium | Backlog | 2026-02-04 09:00 | 162FS | 8 hours | 0 hours | 8 hours | 1 day | No | Once benefit is established, consult with EPA for method to learn implementation
162 | 5.3.3.3 | Orange | Yield - Create implementation framework |  | 2026-02-11 17:00 | 0% |  | EPA | 161FS | Series 1 IBA Development | Medium | Backlog | 2026-02-05 09:00 |  | 40 hours | 0 hours | 40 hours | 5 days | No | Create an implementation framwork that allows us to detect implementation (where possible)
163 | 5.4 | Black | Develop Case Study & Review |  | 2026-03-10 16:00 | 0% |  |  |  |  | Medium |  | 2026-02-12 09:00 |  | 456 hours | 0 hours | 456 hours | 19 days | No
164 | 5.4.1 | Grey | Steam Network Case Study |  | 2026-03-10 16:00 | 0% |  |  |  |  | Medium |  | 2026-02-12 09:00 | 178FS | 152 hours | 0 hours | 152 hours | 19 days | No
165 | 5.4.1.1 | Orange | Steam Case Study - Share with CS |  | 2026-03-03 17:00 | 0% |  | IES | 151FS | Series 1 IBA Development | Medium | Backlog | 2026-02-12 09:00 | 166FS | 112 hours | 0 hours | 112 hours | 14 days | No |  | 0/3 | Receive CS approval;Update content;Share content
166 | 5.4.1.2 | Orange | Steam Case Study - Import |  | 2026-03-05 17:00 | 0% |  | IES | 165FS | Series 1 IBA Development | Medium | Backlog | 2026-03-04 09:00 | 167FS | 16 hours | 0 hours | 16 hours | 2 days | No |  | 0/3 | Import maestro content;Import validation tables;Import maestro graphs
167 | 5.4.1.3 | Orange | Steam Case Study - Check & Proofread |  | 2026-03-10 16:00 | 0% |  | IES;CS | 166FS | Series 1 IBA Development | Medium | Backlog | 2026-03-06 09:00 |  | 24 hours | 0 hours | 24 hours | 3 days | No
168 | 5.4.2 | Grey | Fuel Balance Case Study |  | 2026-03-10 16:00 | 0% |  |  |  |  | Medium |  | 2026-02-12 09:00 | 180FS | 152 hours | 0 hours | 152 hours | 19 days | No
169 | 5.4.2.1 | Orange | Fuel Case Study - Share content with CS |  | 2026-03-03 17:00 | 0% |  | IES | 155FS | Series 1 IBA Development | Medium | Backlog | 2026-02-12 09:00 | 170FS | 112 hours | 0 hours | 112 hours | 14 days | No |  | 0/3 | receive CS approval;Update content;Share content
170 | 5.4.2.2 | Orange | Fuel Case Study - Import |  | 2026-03-05 17:00 | 0% |  | IES | 169FS | Series 1 IBA Development | Medium | Backlog | 2026-03-04 09:00 | 171FS | 16 hours | 0 hours | 16 hours | 2 days | No |  | 0/3 | Import maestro content;Import validation tables;Import maestro graphs
171 | 5.4.2.3 | Orange | Fuel Case Study - Check & Proofread |  | 2026-03-10 16:00 | 0% |  | IES;CS | 170FS | Series 1 IBA Development | Medium | Backlog | 2026-03-06 09:00 |  | 24 hours | 0 hours | 24 hours | 3 days | No
172 | 5.4.3 | Grey | Production Yield Case Study |  | 2026-03-10 16:00 | 0% |  |  |  |  | Medium |  | 2026-02-12 09:00 | 182FS | 152 hours | 0 hours | 152 hours | 19 days | No
173 | 5.4.3.1 | Orange | Yield Case Study - Share content with CS |  | 2026-03-03 17:00 | 0% |  | IES | 159FS | Series 1 IBA Development | Medium | Backlog | 2026-02-12 09:00 | 174FS | 112 hours | 0 hours | 112 hours | 14 days | No |  | 0/3 | Receive CS approval;update content;Share content
174 | 5.4.3.2 | Orange | Yield Case Study - Import |  | 2026-03-05 17:00 | 0% |  | IES | 173FS | Series 1 IBA Development | Medium | Backlog | 2026-03-04 09:00 | 175FS | 16 hours | 0 hours | 16 hours | 2 days | No |  | 0/3 | Import maestro content;Import validation tables;Import maestro graphs
175 | 5.4.3.3 | Orange | Yield Case Study - Check & Proofread |  | 2026-03-10 16:00 | 0% |  | IES;CS | 174FS | Series 1 IBA Development | Medium | Backlog | 2026-03-06 09:00 |  | 24 hours | 0 hours | 24 hours | 3 days | No
176 | 5.5 | Black | Executive Review of IBA Results |  | 2026-03-17 16:00 | 0% |  |  |  |  | Medium |  | 2026-03-11 08:00 | 195FS | 120 hours | 0 hours | 120 hours | 5 days | No
177 | 5.5.1 | Grey | Steam Network IBA Review |  | 2026-03-17 16:00 | 0% |  |  |  |  | Medium |  | 2026-03-11 08:00 |  | 40 hours | 0 hours | 40 hours | 5 days | No
178 | 5.5.1.1 | Orange | Steam - Exec approval of financial benefit |  | 2026-03-17 16:00 | 0% |  | BD;CS;Exec;IES | 164FS | Series 1 IBA Development | Medium | Backlog | 2026-03-11 08:00 | 185FS, 186FS | 40 hours | 0 hours | 40 hours | 5 days | No |  |  |  | Complete POV
179 | 5.5.2 | Grey | Fuel Balance IBA Review |  | 2026-03-17 16:00 | 0% |  |  |  |  | Medium |  | 2026-03-11 08:00 |  | 40 hours | 0 hours | 40 hours | 5 days | No
180 | 5.5.2.1 | Orange | Fuel - Exec approval of financial benefit |  | 2026-03-17 16:00 | 0% |  | BD;CS;Exec;IES | 168FS | Series 1 IBA Development | Medium | Backlog | 2026-03-11 08:00 | 188FS, 189FS | 40 hours | 0 hours | 40 hours | 5 days | No |  |  |  | Complete POV
181 | 5.5.3 | Grey | Production Yield IBA Review |  | 2026-03-17 16:00 | 0% |  |  |  |  | Medium |  | 2026-03-11 08:00 |  | 40 hours | 0 hours | 40 hours | 5 days | No
182 | 5.5.3.1 | Orange | Yield - Exec approval of financial benefit |  | 2026-03-17 16:00 | 0% |  | BD;CS;Exec;IES | 172FS | Series 1 IBA Development | Medium | Backlog | 2026-03-11 08:00 | 191FS, 192FS | 40 hours | 0 hours | 40 hours | 5 days | No |  |  |  | Complete POV
183 | 5.6 | Black | Develop IBA Deck |  | 2026-03-24 16:00 | 0% |  |  |  |  | Medium |  | 2026-03-18 08:00 |  | 144 hours | 0 hours | 144 hours | 5 days | No
184 | 5.6.1 | Grey | Steam Network IBA Deck |  | 2026-03-20 16:00 | 0% |  |  |  |  | Medium |  | 2026-03-18 08:00 | 193FS | 48 hours | 0 hours | 48 hours | 3 days | No
185 | 5.6.1.1 | Orange | Steam Deck - Develop design framework |  | 2026-03-20 16:00 | 0% |  | CS;Design | 178FS | Series 1 IBA Development | Medium | Backlog | 2026-03-18 08:00 |  | 24 hours | 0 hours | 24 hours | 3 days | No
186 | 5.6.1.2 | Orange | Steam Deck - Develop storyboard |  | 2026-03-20 16:00 | 0% |  | CS;Design | 178FS | Series 1 IBA Development | Medium | Backlog | 2026-03-18 08:00 |  | 24 hours | 0 hours | 24 hours | 3 days | No
187 | 5.6.2 | Grey | Fuel Balance IBA Deck |  | 2026-03-20 16:00 | 0% |  |  |  |  | Medium |  | 2026-03-18 08:00 | 193FS | 48 hours | 0 hours | 48 hours | 3 days | No
188 | 5.6.2.1 | Orange | Fuel Deck - Develop design framework |  | 2026-03-20 16:00 | 0% |  | CS;Design | 180FS | Series 1 IBA Development | Medium | Backlog | 2026-03-18 08:00 |  | 24 hours | 0 hours | 24 hours | 3 days | No
189 | 5.6.2.2 | Orange | Fuel Deck - Develop storyboard |  | 2026-03-20 16:00 | 0% |  | CS;Design | 180FS | Series 1 IBA Development | Medium | Backlog | 2026-03-18 08:00 |  | 24 hours | 0 hours | 24 hours | 3 days | No
190 | 5.6.3 | Grey | Production Yield IBA Deck |  | 2026-03-20 16:00 | 0% |  |  |  |  | Medium |  | 2026-03-18 08:00 | 193FS | 48 hours | 0 hours | 48 hours | 3 days | No
191 | 5.6.3.1 | Orange | Yield Deck - Develop design framework |  | 2026-03-20 16:00 | 0% |  | CS;Design | 182FS | Series 1 IBA Development | Medium | Backlog | 2026-03-18 08:00 |  | 24 hours | 0 hours | 24 hours | 3 days | No
192 | 5.6.3.2 | Orange | Yield Deck - Develop storyboard |  | 2026-03-20 16:00 | 0% |  | CS;Design | 182FS | Series 1 IBA Development | Medium | Backlog | 2026-03-18 08:00 |  | 24 hours | 0 hours | 24 hours | 3 days | No
193 | 5.6.4 | Orange | Series 1 - Complete IBA Deck |  | 2026-03-23 16:00 | 0% |  | IES;CS | 187FS, 190FS, 184FS | Pre-Kick Off Planning | Medium | Backlog | 2026-03-23 08:00 | 194FS |  |  |  | 1 day | No
194 | 5.6.5 | Orange | Series 1 - IBA Deck - Executive Review |  | 2026-03-24 16:00 | 0% |  | Exec | 193FS | Pre-Kick Off Planning | Medium | Backlog | 2026-03-24 08:00 |  |  |  |  | 1 day | No |  |  |  | Complete POV
195 | 5.6.6 | Orange | Series 1 - POV Portal - Executive Review |  | 2026-03-18 16:00 | 0% |  | Exec | 176FS | Pre-Kick Off Planning | Medium | Backlog | 2026-03-18 08:00 |  |  |  |  | 1 day | No |  |  |  | Complete POV
196 | 6 | Black Outline | Series 2 IBA Development |  | 2026-06-24 16:00 | 0% |  |  | 110FS |  | Medium |  | 2026-03-25 08:00 | 282FS | 880 hours | 0 hours | 880 hours | 66 days | No
197 | 6.1 | Black | Data Qualification |  | 2026-05-29 16:00 | 0% |  |  | 84FS |  | Medium |  | 2026-03-25 08:00 |  | 128 hours | 0 hours | 128 hours | 48 days | No
198 | 6.1.1 | Grey | Feedstock Utilization Data Qualification |  | 2026-04-03 16:00 | 0% |  |  |  |  | Medium |  | 2026-03-25 08:00 | 215FS | 64 hours | 0 hours | 64 hours | 8 days | No
199 | 6.1.1.1 | Orange | Feedstock - Establish Data Connection |  | 2026-03-25 16:00 | 0% |  | IES;R&D;DS |  | Series 2 IBA Development | Medium | Backlog | 2026-03-25 08:00 | 200FS | 8 hours | 0 hours | 8 hours | 1 day | No | Establish data connection to SQL database and server | 0/2 | R&D grants permissions to necessary members;Send list of DS/IES members that need permissions to R&D
200 | 6.1.1.2 | Orange | Feedstock - Validate Data |  | 2026-03-30 16:00 | 0% |  | IES | 199FS | Series 2 IBA Development | Medium | Backlog | 2026-03-26 08:00 | 201FS | 24 hours | 0 hours | 24 hours | 3 days | No | Use the DRT to determine the list of data requirements for series 1. | 0/3 | Confirm Validity of data;Agree the official receipt of data required to launch;Determine the list of data requirements
201 | 6.1.1.3 | Orange | Feedstock - Check Data Availability |  | 2026-04-02 16:00 | 0% |  | DS | 200FS | Series 2 IBA Development | Medium | Backlog | 2026-03-31 08:00 | 202FS | 24 hours | 0 hours | 24 hours | 3 days | No | Run alaysis to check for data availability per tag and per time stamp | 0/3 | Close dta qualification after sign-off point is reached;Check data health;Check data availability
202 | 6.1.1.4 | Orange | Feedstock - Mark Receipt of Each Data Source |  | 2026-04-03 16:00 | 0% |  | IES | 201FS | Series 2 IBA Development | Medium | Backlog | 2026-04-03 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | On receipt of data, mark recept against each previously afreed data source for the benefit idea
203 | 6.1.2 | Grey | Product Quality Data Qualification |  | 2026-05-29 16:00 | 0% |  |  | 250FS |  | Medium |  | 2026-05-26 08:00 | 222FS | 32 hours | 0 hours | 32 hours | 4 days | No
204 | 6.1.2.1 | Orange | Quality - Establish Data Connection |  | 2026-05-26 16:00 | 0% |  | IES;R&D;DS |  | Series 2 IBA Development | Medium | Backlog | 2026-05-26 08:00 | 205FS | 8 hours | 0 hours | 8 hours | 1 day | No | Establish data connection to SQL database and server | 0/2 | R&D grants permissions to necessary members;Send list of DS/IES members that need permissions to R&D
205 | 6.1.2.2 | Orange | Quality - Validate Data |  | 2026-05-27 16:00 | 0% |  | IES | 204FS | Series 2 IBA Development | Medium | Backlog | 2026-05-27 08:00 | 206FS | 8 hours | 0 hours | 8 hours | 1 day | No | Use the DRT to determine the list of data requirements for series 1. | 0/3 | Confirm Validity of data;Agree the official receipt of data required to launch;Determine the list of data requirements
206 | 6.1.2.3 | Orange | Quality - Check Data Availability |  | 2026-05-28 16:00 | 0% |  | DS | 205FS | Series 2 IBA Development | Medium | Backlog | 2026-05-28 08:00 | 207FS | 8 hours | 0 hours | 8 hours | 1 day | No | Run alaysis to check for data availability per tag and per time stamp | 0/3 | Close dta qualification after sign-off point is reached;Check data health;Check data availability
207 | 6.1.2.4 | Orange | Quality - Mark Receipt of Each Data Source |  | 2026-05-29 16:00 | 0% |  | IES | 206FS | Series 2 IBA Development | Medium | Backlog | 2026-05-29 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | On receipt of data, mark recept against each previously afreed data source for the benefit idea
208 | 6.1.3 | Grey | Product Transition Data Qualification |  | 2026-05-29 16:00 | 0% |  |  | 250FS |  | Medium |  | 2026-05-26 08:00 | 229FS | 32 hours | 0 hours | 32 hours | 4 days | No
209 | 6.1.3.1 | Orange | Product Transition - Establish Data Connection |  | 2026-05-26 16:00 | 0% |  | IES;R&D;DS |  | Series 2 IBA Development | Medium | Backlog | 2026-05-26 08:00 | 210FS | 8 hours | 0 hours | 8 hours | 1 day | No | Establish data connection to SQL database and server | 0/2 | R&D grants permissions to necessary members;Send list of DS/IES members that need permissions to R&D
210 | 6.1.3.2 | Orange | Product Transition - Validate Data |  | 2026-05-27 16:00 | 0% |  | IES | 209FS | Series 2 IBA Development | Medium | Backlog | 2026-05-27 08:00 | 211FS | 8 hours | 0 hours | 8 hours | 1 day | No | Use the DRT to determine the list of data requirements for series 1. | 0/3 | Confirm Validity of data;Agree the official receipt of data required to launch;Determine the list of data requirements
211 | 6.1.3.3 | Orange | Product Transition - Check Data Availability |  | 2026-05-28 16:00 | 0% |  | DS | 210FS | Series 2 IBA Development | Medium | Backlog | 2026-05-28 08:00 | 212FS | 8 hours | 0 hours | 8 hours | 1 day | No | Run alaysis to check for data availability per tag and per time stamp | 0/3 | Close dta qualification after sign-off point is reached;Check data health;Check data availability
212 | 6.1.3.4 | Orange | Product Transition - Mark Receipt of Each Data Source |  | 2026-05-29 16:00 | 0% |  | IES | 211FS | Series 2 IBA Development | Medium | Backlog | 2026-05-29 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | On receipt of data, mark recept against each previously afreed data source for the benefit idea
213 | 6.2 | Black | Digital Twin, Mapping and Prediction |  | 2026-06-16 16:00 | 0% |  |  |  |  | Medium |  | 2026-04-06 08:00 |  | 296 hours | 0 hours | 296 hours | 52 days | No
214 | 6.2.1 | Grey | Feedstock Utilization Digital Twin |  | 2026-04-20 16:00 | 0% |  |  |  |  | Medium |  | 2026-04-06 08:00 | 235FS | 96 hours | 0 hours | 96 hours | 11 days | No
215 | 6.2.1.1 | Orange | Feedstock - Determine relevant tags & target |  | 2026-04-08 16:00 | 0% |  | IES | 198FS | Series 2 IBA Development | Medium | Backlog | 2026-04-06 08:00 | 216FS, 217FS | 24 hours | 0 hours | 24 hours | 3 days | No | For each major unit find all relevant tags for DS to use in a correlation analysis | 0/2 | Provide target KPIs;Determine relevant tags for model
216 | 6.2.1.2 | Orange | Feedstock - DS KT session |  | 2026-04-09 16:00 | 0% |  | IES | 215FS | Series 2 IBA Development | Medium | Backlog | 2026-04-09 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | Sign off the data science KT session where optimization objectives are known | 0/2 | Have DS KT session;Create DS KT documents
217 | 6.2.1.3 | Orange | Feedstock - Label tags for the models |  | 2026-04-13 16:00 | 0% |  | IES;DS | 215FS | Series 2 IBA Development | Medium | Backlog | 2026-04-09 08:00 | 218FS | 24 hours | 0 hours | 24 hours | 3 days | No | Use process documentation to list control. manipulated, disturbance & constraint tags for each unit. Where possible have DS complete automated list
218 | 6.2.1.4 | Orange | Feedstock - Create Bounds & Changing Rates |  | 2026-04-14 16:00 | 0% |  | IES;DS | 217FS | Series 2 IBA Development | Medium | Backlog | 2026-04-14 08:00 | 219FS | 8 hours | 0 hours | 8 hours | 1 day | No | IES or DS task. IES would manually look at historical data or DS could create script to determine bounds and changing rates. | 0/3 | Validate based on process knowledge;Create changing rates;Create bounds
219 | 6.2.1.5 | Orange | Feedstock - Generate model |  | 2026-04-15 16:00 | 0% |  | DS | 218FS | Series 2 IBA Development | Medium | Backlog | 2026-04-15 08:00 | 220FS, 238FS | 8 hours | 0 hours | 8 hours | 1 day | No |  | 0/4 | Get the validation supporting by referring the historical data;Get the model accrucary and confirm with IES team;Get historical optimized directives;Create a model for predicting the target
220 | 6.2.1.6 | Orange | Feedstock - Ensure correct formatting and that data is uploaded to Maestro |  | 2026-04-20 16:00 | 0% |  | IES;R&D | 219FS | Series 2 IBA Development | Medium | Backlog | 2026-04-16 08:00 |  | 24 hours | 0 hours | 24 hours | 3 days | No
221 | 6.2.2 | Grey | Product Quality Digital Twin |  | 2026-06-15 16:00 | 0% |  |  |  |  | Medium |  | 2026-06-01 08:00 | 235FS | 96 hours | 0 hours | 96 hours | 11 days | No
222 | 6.2.2.1 | Orange | Quality - Determine relevant tags & target |  | 2026-06-03 16:00 | 0% |  | IES | 203FS | Series 2 IBA Development | Medium | Backlog | 2026-06-01 08:00 | 223FS, 224FS | 24 hours | 0 hours | 24 hours | 3 days | No | For each major unit find all relevant tags for DS to use in a correlation analysis | 0/2 | Provide target KPIs;Determine relevant tags for model
223 | 6.2.2.2 | Orange | Quality - DS KT session |  | 2026-06-04 16:00 | 0% |  | IES | 222FS | Series 2 IBA Development | Medium | Backlog | 2026-06-04 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | Sign off the data science KT session where optimization objectives are known | 0/2 | Have DS KT session;Create DS KT documents
224 | 6.2.2.3 | Orange | Quality - Label tags for the models |  | 2026-06-08 16:00 | 0% |  | IES;DS | 222FS | Series 2 IBA Development | Medium | Backlog | 2026-06-04 08:00 | 225FS | 24 hours | 0 hours | 24 hours | 3 days | No | Use process documentation to list control. manipulated, disturbance & constraint tags for each unit. Where possible have DS complete automated list
225 | 6.2.2.4 | Orange | Quality - Create Bounds & Changing Rates |  | 2026-06-09 16:00 | 0% |  | IES;DS | 224FS | Series 2 IBA Development | Medium | Backlog | 2026-06-09 08:00 | 226FS | 8 hours | 0 hours | 8 hours | 1 day | No | IES or DS task. IES would manually look at historical data or DS could create script to determine bounds and changing rates. | 0/3 | Validate based on process knowledge;Create changing rates;Create bounds
226 | 6.2.2.5 | Orange | Quality - Generate model |  | 2026-06-10 16:00 | 0% |  | DS | 225FS | Series 2 IBA Development | Medium | Backlog | 2026-06-10 08:00 | 227FS, 242FS | 8 hours | 0 hours | 8 hours | 1 day | No |  | 0/4 | Get the validation supporting by referring the historical data;Get the model accrucary and confirm with IES team;Get historical optimized directives;Create a model for predicting the target
227 | 6.2.2.6 | Orange | Quality - Ensure correct formatting and that data is uploaded to Maestro |  | 2026-06-15 16:00 | 0% |  | IES;R&D | 226FS | Series 2 IBA Development | Medium | Backlog | 2026-06-11 08:00 |  | 24 hours | 0 hours | 24 hours | 3 days | No
228 | 6.2.3 | Grey | Product Transition Digital Twin |  | 2026-06-15 16:00 | 0% |  |  |  |  | Medium |  | 2026-06-01 08:00 | 235FS | 96 hours | 0 hours | 96 hours | 11 days | No
229 | 6.2.3.1 | Orange | Product Transition - Determine relevant tags & target |  | 2026-06-03 16:00 | 0% |  | IES | 208FS | Series 2 IBA Development | Medium | Backlog | 2026-06-01 08:00 | 230FS, 231FS | 24 hours | 0 hours | 24 hours | 3 days | No | For each major unit find all relevant tags for DS to use in a correlation analysis | 0/2 | Provide target KPIs;Determine relevant tags for model
230 | 6.2.3.2 | Orange | Product Transition - DS KT session |  | 2026-06-04 16:00 | 0% |  | IES | 229FS | Series 2 IBA Development | Medium | Backlog | 2026-06-04 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | Sign off the data science KT session where optimization objectives are known | 0/2 | Have DS KT session;Create DS KT documents
231 | 6.2.3.3 | Orange | Product Transition - Label tags for the models |  | 2026-06-08 16:00 | 0% |  | IES;DS | 229FS | Series 2 IBA Development | Medium | Backlog | 2026-06-04 08:00 | 232FS | 24 hours | 0 hours | 24 hours | 3 days | No | Use process documentation to list control. manipulated, disturbance & constraint tags for each unit. Where possible have DS complete automated list
232 | 6.2.3.4 | Orange | Product Transition - Create Bounds & Changing Rates |  | 2026-06-09 16:00 | 0% |  | IES;DS | 231FS | Series 2 IBA Development | Medium | Backlog | 2026-06-09 08:00 | 233FS | 8 hours | 0 hours | 8 hours | 1 day | No | IES or DS task. IES would manually look at historical data or DS could create script to determine bounds and changing rates. | 0/3 | Validate based on process knowledge;Create changing rates;Create bounds
233 | 6.2.3.5 | Orange | Product Transition - Generate model |  | 2026-06-10 16:00 | 0% |  | DS | 232FS | Series 2 IBA Development | Medium | Backlog | 2026-06-10 08:00 | 234FS, 246FS | 8 hours | 0 hours | 8 hours | 1 day | No |  | 0/4 | Get the validation supporting by referring the historical data;Get the model accrucary and confirm with IES team;Get historical optimized directives;Create a model for predicting the target
234 | 6.2.3.6 | Orange | Product Transition - Ensure correct formatting and that data is uploaded to Maestro |  | 2026-06-15 16:00 | 0% |  | IES;R&D | 233FS | Series 2 IBA Development | Medium | Backlog | 2026-06-11 08:00 |  | 24 hours | 0 hours | 24 hours | 3 days | No
235 | 6.2.4 | Orange | Stack Series LSTM Models |  | 2026-06-16 16:00 | 0% |  | DS | 214FS, 221FS, 228FS | Series 2 IBA Development | Medium | Backlog | 2026-06-16 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | Stack the models for all the use cases
236 | 6.3 | Black | Benefit Quantification |  | 2026-06-15 16:00 | 0% |  |  |  |  | Medium |  | 2026-04-16 08:00 |  | 120 hours | 0 hours | 120 hours | 43 days | No
237 | 6.3.1 | Grey | Feedstock Utilization Benefit Quantification |  | 2026-04-28 16:00 | 0% |  |  |  |  | Medium |  | 2026-04-16 08:00 | 251FS | 72 hours | 0 hours | 72 hours | 9 days | No
238 | 6.3.1.1 | Orange | Feedstock - Establish benefit measurement methodology |  | 2026-04-20 16:00 | 0% |  | IES | 219FS | Series 2 IBA Development | Medium | Backlog | 2026-04-16 08:00 | 239FS | 24 hours | 0 hours | 24 hours | 3 days | No
239 | 6.3.1.2 | Orange | Feedstock - Consult with EPA to learn implementation |  | 2026-04-21 16:00 | 0% |  | EPA;Exec;IES | 238FS | Series 2 IBA Development | Medium | Backlog | 2026-04-21 08:00 | 240FS | 8 hours | 0 hours | 8 hours | 1 day | No | Once benefit is established, consult with EPA for method to learn implementation
240 | 6.3.1.3 | Orange | Feedstock - Create implementation framework |  | 2026-04-28 16:00 | 0% |  | EPA | 239FS | Series 2 IBA Development | Medium | Backlog | 2026-04-22 08:00 |  | 40 hours | 0 hours | 40 hours | 5 days | No | Create an implementation framwork that allows us to detect implementation (where possible)
241 | 6.3.2 | Grey | Product Quality Benefit Quantification |  | 2026-06-15 16:00 | 0% |  |  |  |  | Medium |  | 2026-06-11 08:00 | 255FS | 24 hours | 0 hours | 24 hours | 3 days | No
242 | 6.3.2.1 | Orange | Quality - Establish benefit measurement methodology |  | 2026-06-11 16:00 | 0% |  | IES | 226FS | Series 2 IBA Development | Medium | Backlog | 2026-06-11 08:00 | 243FS | 8 hours | 0 hours | 8 hours | 1 day | No
243 | 6.3.2.2 | Orange | Quality - Consult with EPA to learn implementation |  | 2026-06-12 16:00 | 0% |  | EPA;Exec;IES | 242FS | Series 2 IBA Development | Medium | Backlog | 2026-06-12 08:00 | 244FS | 8 hours | 0 hours | 8 hours | 1 day | No | Once benefit is established, consult with EPA for method to learn implementation
244 | 6.3.2.3 | Orange | Quality - Create implementation framework |  | 2026-06-15 16:00 | 0% |  | EPA | 243FS | Series 2 IBA Development | Medium | Backlog | 2026-06-15 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | Create an implementation framwork that allows us to detect implementation (where possible)
245 | 6.3.3 | Grey | Product Transition Benefit Quantification |  | 2026-06-15 16:00 | 0% |  |  |  |  | Medium |  | 2026-06-11 08:00 | 259FS | 24 hours | 0 hours | 24 hours | 3 days | No
246 | 6.3.3.1 | Orange | Product Transition - Establish benefit measurement methodology |  | 2026-06-11 16:00 | 0% |  | IES | 233FS | Series 2 IBA Development | Medium | Backlog | 2026-06-11 08:00 | 247FS | 8 hours | 0 hours | 8 hours | 1 day | No
247 | 6.3.3.2 | Orange | Product Transition - Consult with EPA to learn implementation |  | 2026-06-12 16:00 | 0% |  | EPA;Exec;IES | 246FS | Series 2 IBA Development | Medium | Backlog | 2026-06-12 08:00 | 248FS | 8 hours | 0 hours | 8 hours | 1 day | No | Once benefit is established, consult with EPA for method to learn implementation
248 | 6.3.3.3 | Orange | Product Transition - Create implementation framework |  | 2026-06-15 16:00 | 0% |  | EPA | 247FS | Series 2 IBA Development | Medium | Backlog | 2026-06-15 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | Create an implementation framwork that allows us to detect implementation (where possible)
249 | 6.4 | Black | Develop Case Study & Review |  | 2026-06-18 16:00 | 0% |  |  |  |  | Medium |  | 2026-04-29 08:00 |  | 200 hours | 0 hours | 200 hours | 37 days | No
250 | 6.4.1 | Grey | Feedstock Utilization Case Study |  | 2026-05-25 16:00 | 0% |  |  |  |  | Medium |  | 2026-04-29 08:00 | 264FS, 203FS, 208FS | 152 hours | 0 hours | 152 hours | 19 days | No
251 | 6.4.1.1 | Orange | Feedstock Case Study - Share with CS |  | 2026-05-18 16:00 | 0% |  | IES | 237FS | Series 2 IBA Development | Medium | Backlog | 2026-04-29 08:00 | 252FS | 112 hours | 0 hours | 112 hours | 14 days | No |  | 0/3 | Receive CS approval;Update content;Share content
252 | 6.4.1.2 | Orange | Feedstock Case Study - Import |  | 2026-05-20 16:00 | 0% |  | IES | 251FS | Series 2 IBA Development | Medium | Backlog | 2026-05-19 08:00 | 253FS | 16 hours | 0 hours | 16 hours | 2 days | No |  | 0/3 | Import maestro content;Import validation tables;Import maestro graphs
253 | 6.4.1.3 | Orange | Feedstock Case Study - Check & Proofread |  | 2026-05-25 16:00 | 0% |  | IES;CS | 252FS | Series 2 IBA Development | Medium | Backlog | 2026-05-21 08:00 |  | 24 hours | 0 hours | 24 hours | 3 days | No
254 | 6.4.2 | Grey | Product Quality Case Study |  | 2026-06-18 16:00 | 0% |  |  |  |  | Medium |  | 2026-06-16 08:00 | 266FS | 24 hours | 0 hours | 24 hours | 3 days | No
255 | 6.4.2.1 | Orange | Quality Case Study - Share content with CS |  | 2026-06-16 16:00 | 0% |  | IES | 241FS | Series 2 IBA Development | Medium | Backlog | 2026-06-16 08:00 | 256FS | 8 hours | 0 hours | 8 hours | 1 day | No |  | 0/3 | receive CS approval;Update content;Share content
256 | 6.4.2.2 | Orange | Quality Case Study - Import |  | 2026-06-17 16:00 | 0% |  | IES | 255FS | Series 2 IBA Development | Medium | Backlog | 2026-06-17 08:00 | 257FS | 8 hours | 0 hours | 8 hours | 1 day | No |  | 0/3 | Import maestro content;Import validation tables;Import maestro graphs
257 | 6.4.2.3 | Orange | Quality Case Study - Check & Proofread |  | 2026-06-18 16:00 | 0% |  | IES;CS | 256FS | Series 2 IBA Development | Medium | Backlog | 2026-06-18 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No
258 | 6.4.3 | Grey | Product Transition Case Study |  | 2026-06-18 16:00 | 0% |  |  |  |  | Medium |  | 2026-06-16 08:00 | 268FS | 24 hours | 0 hours | 24 hours | 3 days | No
259 | 6.4.3.1 | Orange | Product Transition Case Study - Share content with CS |  | 2026-06-16 16:00 | 0% |  | IES | 245FS | Series 2 IBA Development | Medium | Backlog | 2026-06-16 08:00 | 260FS | 8 hours | 0 hours | 8 hours | 1 day | No |  | 0/3 | Receive CS approval;update content;Share content
260 | 6.4.3.2 | Orange | Product Transition Case Study - Import |  | 2026-06-17 16:00 | 0% |  | IES | 259FS | Series 2 IBA Development | Medium | Backlog | 2026-06-17 08:00 | 261FS | 8 hours | 0 hours | 8 hours | 1 day | No |  | 0/3 | Import maestro content;Import validation tables;Import maestro graphs
261 | 6.4.3.3 | Orange | Product Transition Case Study - Check & Proofread |  | 2026-06-18 16:00 | 0% |  | IES;CS | 260FS | Series 2 IBA Development | Medium | Backlog | 2026-06-18 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No
262 | 6.5 | Black | Executive Review of IBA Results |  | 2026-06-19 16:00 | 0% |  |  |  |  | Medium |  | 2026-05-26 08:00 | 281FS | 56 hours | 0 hours | 56 hours | 19 days | No
263 | 6.5.1 | Grey | Feedstock Utilization IBA Review |  | 2026-06-01 16:00 | 0% |  |  |  |  | Medium |  | 2026-05-26 08:00 |  | 40 hours | 0 hours | 40 hours | 5 days | No
264 | 6.5.1.1 | Orange | Feedstock - Exec approval of financial benefit |  | 2026-06-01 16:00 | 0% |  | BD;CS;Exec;IES | 250FS | Series 2 IBA Development | Medium | Backlog | 2026-05-26 08:00 | 271FS, 272FS | 40 hours | 0 hours | 40 hours | 5 days | No |  |  |  | Complete POV
265 | 6.5.2 | Grey | Product Quality IBA Review |  | 2026-06-19 16:00 | 0% |  |  |  |  | Medium |  | 2026-06-19 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No
266 | 6.5.2.1 | Orange | Quality - Exec approval of financial benefit |  | 2026-06-19 16:00 | 0% |  | BD;CS;Exec;IES | 254FS | Series 2 IBA Development | Medium | Backlog | 2026-06-19 08:00 | 274FS, 275FS | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Complete POV
267 | 6.5.3 | Grey | Product Transition IBA Review |  | 2026-06-19 16:00 | 0% |  |  |  |  | Medium |  | 2026-06-19 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No
268 | 6.5.3.1 | Orange | Product Transition - Exec approval of financial benefit |  | 2026-06-19 16:00 | 0% |  | BD;CS;Exec;IES | 258FS | Series 2 IBA Development | Medium | Backlog | 2026-06-19 08:00 | 277FS, 278FS | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Complete POV
269 | 6.6 | Black | Develop IBA Deck |  | 2026-06-24 16:00 | 0% |  |  |  |  | Medium |  | 2026-06-02 08:00 |  | 80 hours | 0 hours | 80 hours | 17 days | No
270 | 6.6.1 | Grey | Feedstock Utilization IBA Deck |  | 2026-06-04 16:00 | 0% |  |  |  |  | Medium |  | 2026-06-02 08:00 | 279FS | 48 hours | 0 hours | 48 hours | 3 days | No
271 | 6.6.1.1 | Orange | Feedstock - Develop design framework |  | 2026-06-04 16:00 | 0% |  | CS;Design | 264FS | Series 2 IBA Development | Medium | Backlog | 2026-06-02 08:00 |  | 24 hours | 0 hours | 24 hours | 3 days | No
272 | 6.6.1.2 | Orange | Feedstock - Develop storyboard |  | 2026-06-04 16:00 | 0% |  | CS;Design | 264FS | Series 2 IBA Development | Medium | Backlog | 2026-06-02 08:00 |  | 24 hours | 0 hours | 24 hours | 3 days | No
273 | 6.6.2 | Grey | Product Quality IBA Deck |  | 2026-06-22 16:00 | 0% |  |  |  |  | Medium |  | 2026-06-22 08:00 | 279FS | 16 hours | 0 hours | 16 hours | 1 day | No
274 | 6.6.2.1 | Orange | Quality - Develop design framework |  | 2026-06-22 16:00 | 0% |  | CS;Design | 266FS | Series 2 IBA Development | Medium | Backlog | 2026-06-22 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No
275 | 6.6.2.2 | Orange | Quality - Develop storyboard |  | 2026-06-22 16:00 | 0% |  | CS;Design | 266FS | Series 2 IBA Development | Medium | Backlog | 2026-06-22 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No
276 | 6.6.3 | Grey | Product Transition IBA Deck |  | 2026-06-22 16:00 | 0% |  |  |  |  | Medium |  | 2026-06-22 08:00 | 279FS | 16 hours | 0 hours | 16 hours | 1 day | No
277 | 6.6.3.1 | Orange | Product Transition Deck - Develop design framework |  | 2026-06-22 16:00 | 0% |  | CS;Design | 268FS | Series 2 IBA Development | Medium | Backlog | 2026-06-22 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No
278 | 6.6.3.2 | Orange | Product Transition Deck - Develop storyboard |  | 2026-06-22 16:00 | 0% |  | CS;Design | 268FS | Series 2 IBA Development | Medium | Backlog | 2026-06-22 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No
279 | 6.6.4 | Orange | Series 2 - Complete IBA Deck |  | 2026-06-23 16:00 | 0% |  | IES;CS | 270FS, 273FS, 276FS | Pre-Kick Off Planning | Medium | Backlog | 2026-06-23 08:00 | 280FS |  |  |  | 1 day | No
280 | 6.6.5 | Orange | Series 2 - IBA Deck - Executive Review |  | 2026-06-24 16:00 | 0% |  | Exec | 279FS | Pre-Kick Off Planning | Medium | Backlog | 2026-06-24 08:00 |  |  |  |  | 1 day | No |  |  |  | Complete POV
281 | 6.6.6 | Orange | Series 2 - POV Portal - Executive Review |  | 2026-06-22 16:00 | 0% |  | Exec | 262FS | Pre-Kick Off Planning | Medium | Backlog | 2026-06-22 08:00 |  |  |  |  | 1 day | No |  |  |  | Complete POV
282 | 7 | Black Outline | Series 3 IBA Development |  | 2026-09-24 16:00 | 0% |  |  | 196FS |  | Medium |  | 2026-06-25 08:00 | 368FS | 880 hours | 0 hours | 880 hours | 66 days | No
283 | 7.1 | Black | Data Qualification |  | 2026-08-31 16:00 | 0% |  |  | 84FS |  | Medium |  | 2026-06-25 08:00 |  | 128 hours | 0 hours | 128 hours | 48 days | No
284 | 7.1.1 | Grey | Planning & Scheduling Data Qualification |  | 2026-07-06 16:00 | 0% |  |  |  |  | Medium |  | 2026-06-25 08:00 | 301FS | 64 hours | 0 hours | 64 hours | 8 days | No
285 | 7.1.1.1 | Orange | P&S - Establish Data Connection |  | 2026-06-25 16:00 | 0% |  | IES;R&D;DS |  | Series 3 IBA Development | Medium | Backlog | 2026-06-25 08:00 | 286FS | 8 hours | 0 hours | 8 hours | 1 day | No | Establish data connection to SQL database and server | 0/2 | R&D grants permissions to necessary members;Send list of DS/IES members that need permissions to R&D
286 | 7.1.1.2 | Orange | P&S - Validate Data |  | 2026-06-30 16:00 | 0% |  | IES | 285FS | Series 3 IBA Development | Medium | Backlog | 2026-06-26 08:00 | 287FS | 24 hours | 0 hours | 24 hours | 3 days | No | Use the DRT to determine the list of data requirements for series 1. | 0/3 | Confirm Validity of data;Agree the official receipt of data required to launch;Determine the list of data requirements
287 | 7.1.1.3 | Orange | P&S - Check Data Availability |  | 2026-07-03 16:00 | 0% |  | DS | 286FS | Series 3 IBA Development | Medium | Backlog | 2026-07-01 08:00 | 288FS | 24 hours | 0 hours | 24 hours | 3 days | No | Run alaysis to check for data availability per tag and per time stamp | 0/3 | Close dta qualification after sign-off point is reached;Check data health;Check data availability
288 | 7.1.1.4 | Orange | P&S - Mark Receipt of Each Data Source |  | 2026-07-06 16:00 | 0% |  | IES | 287FS | Series 3 IBA Development | Medium | Backlog | 2026-07-06 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | On receipt of data, mark recept against each previously afreed data source for the benefit idea
289 | 7.1.2 | Grey | Asset Health & Maintenance Data Qualification |  | 2026-08-31 16:00 | 0% |  |  | 336FS |  | Medium |  | 2026-08-26 08:00 | 308FS | 32 hours | 0 hours | 32 hours | 4 days | No
290 | 7.1.2.1 | Orange | Maintenance - Establish Data Connection |  | 2026-08-26 16:00 | 0% |  | IES;R&D;DS |  | Series 3 IBA Development | Medium | Backlog | 2026-08-26 08:00 | 291FS | 8 hours | 0 hours | 8 hours | 1 day | No | Establish data connection to SQL database and server | 0/2 | R&D grants permissions to necessary members;Send list of DS/IES members that need permissions to R&D
291 | 7.1.2.2 | Orange | Maintenance - Validate Data |  | 2026-08-27 16:00 | 0% |  | IES | 290FS | Series 3 IBA Development | Medium | Backlog | 2026-08-27 08:00 | 292FS | 8 hours | 0 hours | 8 hours | 1 day | No | Use the DRT to determine the list of data requirements for series 1. | 0/3 | Confirm Validity of data;Agree the official receipt of data required to launch;Determine the list of data requirements
292 | 7.1.2.3 | Orange | Maintenance - Check Data Availability |  | 2026-08-28 16:00 | 0% |  | DS | 291FS | Series 3 IBA Development | Medium | Backlog | 2026-08-28 08:00 | 293FS | 8 hours | 0 hours | 8 hours | 1 day | No | Run alaysis to check for data availability per tag and per time stamp | 0/3 | Close dta qualification after sign-off point is reached;Check data health;Check data availability
293 | 7.1.2.4 | Orange | Maintenance - Mark Receipt of Each Data Source |  | 2026-08-31 16:00 | 0% |  | IES | 292FS | Series 3 IBA Development | Medium | Backlog | 2026-08-31 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | On receipt of data, mark recept against each previously afreed data source for the benefit idea
294 | 7.1.3 | Grey | Plant Resource Efficiency Data Qualification |  | 2026-08-31 16:00 | 0% |  |  | 336FS |  | Medium |  | 2026-08-26 08:00 | 315FS | 32 hours | 0 hours | 32 hours | 4 days | No
295 | 7.1.3.1 | Orange | RE - Establish Data Connection |  | 2026-08-26 16:00 | 0% |  | IES;R&D;DS |  | Series 3 IBA Development | Medium | Backlog | 2026-08-26 08:00 | 296FS | 8 hours | 0 hours | 8 hours | 1 day | No | Establish data connection to SQL database and server | 0/2 | R&D grants permissions to necessary members;Send list of DS/IES members that need permissions to R&D
296 | 7.1.3.2 | Orange | RE - Validate Data |  | 2026-08-27 16:00 | 0% |  | IES | 295FS | Series 3 IBA Development | Medium | Backlog | 2026-08-27 08:00 | 297FS | 8 hours | 0 hours | 8 hours | 1 day | No | Use the DRT to determine the list of data requirements for series 1. | 0/3 | Confirm Validity of data;Agree the official receipt of data required to launch;Determine the list of data requirements
297 | 7.1.3.3 | Orange | RE - Check Data Availability |  | 2026-08-28 16:00 | 0% |  | DS | 296FS | Series 3 IBA Development | Medium | Backlog | 2026-08-28 08:00 | 298FS | 8 hours | 0 hours | 8 hours | 1 day | No | Run alaysis to check for data availability per tag and per time stamp | 0/3 | Close dta qualification after sign-off point is reached;Check data health;Check data availability
298 | 7.1.3.4 | Orange | RE - Mark Receipt of Each Data Source |  | 2026-08-31 16:00 | 0% |  | IES | 297FS | Series 3 IBA Development | Medium | Backlog | 2026-08-31 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | On receipt of data, mark recept against each previously afreed data source for the benefit idea
299 | 7.2 | Black | Digital Twin, Mapping and Prediction |  | 2026-09-16 16:00 | 0% |  |  |  |  | Medium |  | 2026-07-07 08:00 |  | 296 hours | 0 hours | 296 hours | 52 days | No
300 | 7.2.1 | Grey | Planning & Scheduling Digital Twin |  | 2026-07-21 16:00 | 0% |  |  |  |  | Medium |  | 2026-07-07 08:00 | 321FS | 96 hours | 0 hours | 96 hours | 11 days | No
301 | 7.2.1.1 | Orange | P&S - Determine relevant tags & target |  | 2026-07-09 16:00 | 0% |  | IES | 284FS | Series 3 IBA Development | Medium | Backlog | 2026-07-07 08:00 | 302FS, 303FS | 24 hours | 0 hours | 24 hours | 3 days | No | For each major unit find all relevant tags for DS to use in a correlation analysis | 0/2 | Provide target KPIs;Determine relevant tags for model
302 | 7.2.1.2 | Orange | P&S - DS KT session |  | 2026-07-10 16:00 | 0% |  | IES | 301FS | Series 3 IBA Development | Medium | Backlog | 2026-07-10 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | Sign off the data science KT session where optimization objectives are known | 0/2 | Have DS KT session;Create DS KT documents
303 | 7.2.1.3 | Orange | P&S - Label tags for the models |  | 2026-07-14 16:00 | 0% |  | IES;DS | 301FS | Series 3 IBA Development | Medium | Backlog | 2026-07-10 08:00 | 304FS | 24 hours | 0 hours | 24 hours | 3 days | No | Use process documentation to list control. manipulated, disturbance & constraint tags for each unit. Where possible have DS complete automated list
304 | 7.2.1.4 | Orange | P&S - Create Bounds & Changing Rates |  | 2026-07-15 16:00 | 0% |  | IES;DS | 303FS | Series 3 IBA Development | Medium | Backlog | 2026-07-15 08:00 | 305FS | 8 hours | 0 hours | 8 hours | 1 day | No | IES or DS task. IES would manually look at historical data or DS could create script to determine bounds and changing rates. | 0/3 | Validate based on process knowledge;Create changing rates;Create bounds
305 | 7.2.1.5 | Orange | P&S - Generate model |  | 2026-07-16 16:00 | 0% |  | DS | 304FS | Series 3 IBA Development | Medium | Backlog | 2026-07-16 08:00 | 306FS, 324FS | 8 hours | 0 hours | 8 hours | 1 day | No |  | 0/4 | Get the validation supporting by referring the historical data;Get the model accrucary and confirm with IES team;Get historical optimized directives;Create a model for predicting the target
306 | 7.2.1.6 | Orange | P&S - Ensure correct formatting and that data is uploaded to Maestro |  | 2026-07-21 16:00 | 0% |  | IES;R&D | 305FS | Series 3 IBA Development | Medium | Backlog | 2026-07-17 08:00 |  | 24 hours | 0 hours | 24 hours | 3 days | No
307 | 7.2.2 | Grey | Asset Health & Maintenance Digital Twin |  | 2026-09-15 16:00 | 0% |  |  |  |  | Medium |  | 2026-09-01 08:00 | 321FS | 96 hours | 0 hours | 96 hours | 11 days | No
308 | 7.2.2.1 | Orange | Maintenance - Determine relevant tags & target |  | 2026-09-03 16:00 | 0% |  | IES | 289FS | Series 3 IBA Development | Medium | Backlog | 2026-09-01 08:00 | 309FS, 310FS | 24 hours | 0 hours | 24 hours | 3 days | No | For each major unit find all relevant tags for DS to use in a correlation analysis | 0/2 | Provide target KPIs;Determine relevant tags for model
309 | 7.2.2.2 | Orange | Maintenance - DS KT session |  | 2026-09-04 16:00 | 0% |  | IES | 308FS | Series 3 IBA Development | Medium | Backlog | 2026-09-04 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | Sign off the data science KT session where optimization objectives are known | 0/2 | Have DS KT session;Create DS KT documents
310 | 7.2.2.3 | Orange | Maintenance - Label tags for the models |  | 2026-09-08 16:00 | 0% |  | IES;DS | 308FS | Series 3 IBA Development | Medium | Backlog | 2026-09-04 08:00 | 311FS | 24 hours | 0 hours | 24 hours | 3 days | No | Use process documentation to list control. manipulated, disturbance & constraint tags for each unit. Where possible have DS complete automated list
311 | 7.2.2.4 | Orange | Maintenance - Create Bounds & Changing Rates |  | 2026-09-09 16:00 | 0% |  | IES;DS | 310FS | Series 3 IBA Development | Medium | Backlog | 2026-09-09 08:00 | 312FS | 8 hours | 0 hours | 8 hours | 1 day | No | IES or DS task. IES would manually look at historical data or DS could create script to determine bounds and changing rates. | 0/3 | Validate based on process knowledge;Create changing rates;Create bounds
312 | 7.2.2.5 | Orange | Maintenance - Generate model |  | 2026-09-10 16:00 | 0% |  | DS | 311FS | Series 3 IBA Development | Medium | Backlog | 2026-09-10 08:00 | 313FS, 328FS | 8 hours | 0 hours | 8 hours | 1 day | No |  | 0/4 | Get the validation supporting by referring the historical data;Get the model accrucary and confirm with IES team;Get historical optimized directives;Create a model for predicting the target
313 | 7.2.2.6 | Orange | Maintenance - Ensure correct formatting and that data is uploaded to Maestro |  | 2026-09-15 16:00 | 0% |  | IES;R&D | 312FS | Series 3 IBA Development | Medium | Backlog | 2026-09-11 08:00 |  | 24 hours | 0 hours | 24 hours | 3 days | No
314 | 7.2.3 | Grey | Plant Resource Efficiency Digital Twin |  | 2026-09-15 16:00 | 0% |  |  |  |  | Medium |  | 2026-09-01 08:00 | 321FS | 96 hours | 0 hours | 96 hours | 11 days | No
315 | 7.2.3.1 | Orange | RE - Determine relevant tags & target |  | 2026-09-03 16:00 | 0% |  | IES | 294FS | Series 3 IBA Development | Medium | Backlog | 2026-09-01 08:00 | 316FS, 317FS | 24 hours | 0 hours | 24 hours | 3 days | No | For each major unit find all relevant tags for DS to use in a correlation analysis | 0/2 | Provide target KPIs;Determine relevant tags for model
316 | 7.2.3.2 | Orange | RE - DS KT session |  | 2026-09-04 16:00 | 0% |  | IES | 315FS | Series 3 IBA Development | Medium | Backlog | 2026-09-04 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | Sign off the data science KT session where optimization objectives are known | 0/2 | Have DS KT session;Create DS KT documents
317 | 7.2.3.3 | Orange | RE - Label tags for the models |  | 2026-09-08 16:00 | 0% |  | IES;DS | 315FS | Series 3 IBA Development | Medium | Backlog | 2026-09-04 08:00 | 318FS | 24 hours | 0 hours | 24 hours | 3 days | No | Use process documentation to list control. manipulated, disturbance & constraint tags for each unit. Where possible have DS complete automated list
318 | 7.2.3.4 | Orange | RE - Create Bounds & Changing Rates |  | 2026-09-09 16:00 | 0% |  | IES;DS | 317FS | Series 3 IBA Development | Medium | Backlog | 2026-09-09 08:00 | 319FS | 8 hours | 0 hours | 8 hours | 1 day | No | IES or DS task. IES would manually look at historical data or DS could create script to determine bounds and changing rates. | 0/3 | Validate based on process knowledge;Create changing rates;Create bounds
319 | 7.2.3.5 | Orange | RE - Generate model |  | 2026-09-10 16:00 | 0% |  | DS | 318FS | Series 3 IBA Development | Medium | Backlog | 2026-09-10 08:00 | 320FS, 332FS | 8 hours | 0 hours | 8 hours | 1 day | No |  | 0/4 | Get the validation supporting by referring the historical data;Get the model accrucary and confirm with IES team;Get historical optimized directives;Create a model for predicting the target
320 | 7.2.3.6 | Orange | RE - Ensure correct formatting and that data is uploaded to Maestro |  | 2026-09-15 16:00 | 0% |  | IES;R&D | 319FS | Series 3 IBA Development | Medium | Backlog | 2026-09-11 08:00 |  | 24 hours | 0 hours | 24 hours | 3 days | No
321 | 7.2.4 | Orange | Stack Series LSTM Models |  | 2026-09-16 16:00 | 0% |  | DS | 300FS, 307FS, 314FS | Series 3 IBA Development | Medium | Backlog | 2026-09-16 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | Stack the models for all the use cases
322 | 7.3 | Black | Benefit Quantification |  | 2026-09-15 16:00 | 0% |  |  |  |  | Medium |  | 2026-07-17 08:00 |  | 120 hours | 0 hours | 120 hours | 43 days | No
323 | 7.3.1 | Grey | Planning & Scheduling Benefit Quantification |  | 2026-07-29 16:00 | 0% |  |  |  |  | Medium |  | 2026-07-17 08:00 | 337FS | 72 hours | 0 hours | 72 hours | 9 days | No
324 | 7.3.1.1 | Orange | P&S - Establish benefit measurement methodology |  | 2026-07-21 16:00 | 0% |  | IES | 305FS | Series 3 IBA Development | Medium | Backlog | 2026-07-17 08:00 | 325FS | 24 hours | 0 hours | 24 hours | 3 days | No
325 | 7.3.1.2 | Orange | P&S - Consult with EPA to learn implementation |  | 2026-07-22 16:00 | 0% |  | EPA;Exec;IES | 324FS | Series 3 IBA Development | Medium | Backlog | 2026-07-22 08:00 | 326FS | 8 hours | 0 hours | 8 hours | 1 day | No | Once benefit is established, consult with EPA for method to learn implementation
326 | 7.3.1.3 | Orange | P&S - Create implementation framework |  | 2026-07-29 16:00 | 0% |  | EPA | 325FS | Series 3 IBA Development | Medium | Backlog | 2026-07-23 08:00 |  | 40 hours | 0 hours | 40 hours | 5 days | No | Create an implementation framwork that allows us to detect implementation (where possible)
327 | 7.3.2 | Grey | Asset Health & Maintenance Benefit Quantification |  | 2026-09-15 16:00 | 0% |  |  |  |  | Medium |  | 2026-09-11 08:00 | 341FS | 24 hours | 0 hours | 24 hours | 3 days | No
328 | 7.3.2.1 | Orange | Maintenance - Establish benefit measurement methodology |  | 2026-09-11 16:00 | 0% |  | IES | 312FS | Series 3 IBA Development | Medium | Backlog | 2026-09-11 08:00 | 329FS | 8 hours | 0 hours | 8 hours | 1 day | No
329 | 7.3.2.2 | Orange | Maintenance - Consult with EPA to learn implementation |  | 2026-09-14 16:00 | 0% |  | EPA;Exec;IES | 328FS | Series 3 IBA Development | Medium | Backlog | 2026-09-14 08:00 | 330FS | 8 hours | 0 hours | 8 hours | 1 day | No | Once benefit is established, consult with EPA for method to learn implementation
330 | 7.3.2.3 | Orange | Maintenance - Create implementation framework |  | 2026-09-15 16:00 | 0% |  | EPA | 329FS | Series 3 IBA Development | Medium | Backlog | 2026-09-15 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | Create an implementation framwork that allows us to detect implementation (where possible)
331 | 7.3.3 | Grey | Plant Resource Efficiency Benefit Quantification |  | 2026-09-15 16:00 | 0% |  |  |  |  | Medium |  | 2026-09-11 08:00 | 345FS | 24 hours | 0 hours | 24 hours | 3 days | No
332 | 7.3.3.1 | Orange | RE - Establish benefit measurement methodology |  | 2026-09-11 16:00 | 0% |  | IES | 319FS | Series 3 IBA Development | Medium | Backlog | 2026-09-11 08:00 | 333FS | 8 hours | 0 hours | 8 hours | 1 day | No
333 | 7.3.3.2 | Orange | RE - Consult with EPA to learn implementation |  | 2026-09-14 16:00 | 0% |  | EPA;Exec;IES | 332FS | Series 3 IBA Development | Medium | Backlog | 2026-09-14 08:00 | 334FS | 8 hours | 0 hours | 8 hours | 1 day | No | Once benefit is established, consult with EPA for method to learn implementation
334 | 7.3.3.3 | Orange | RE - Create implementation framework |  | 2026-09-15 16:00 | 0% |  | EPA | 333FS | Series 3 IBA Development | Medium | Backlog | 2026-09-15 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | Create an implementation framwork that allows us to detect implementation (where possible)
335 | 7.4 | Black | Develop Case Study & Review |  | 2026-09-18 16:00 | 0% |  |  |  |  | Medium |  | 2026-07-30 08:00 |  | 200 hours | 0 hours | 200 hours | 37 days | No
336 | 7.4.1 | Grey | Planning & Scheduling Case Study |  | 2026-08-25 16:00 | 0% |  |  |  |  | Medium |  | 2026-07-30 08:00 | 350FS, 289FS, 294FS | 152 hours | 0 hours | 152 hours | 19 days | No
337 | 7.4.1.1 | Orange | P&S Case Study - Share with CS |  | 2026-08-18 16:00 | 0% |  | IES | 323FS | Series 3 IBA Development | Medium | Backlog | 2026-07-30 08:00 | 338FS | 112 hours | 0 hours | 112 hours | 14 days | No |  | 0/3 | Receive CS approval;Update content;Share content
338 | 7.4.1.2 | Orange | P&S Case Study - Import |  | 2026-08-20 16:00 | 0% |  | IES | 337FS | Series 3 IBA Development | Medium | Backlog | 2026-08-19 08:00 | 339FS | 16 hours | 0 hours | 16 hours | 2 days | No |  | 0/3 | Import maestro content;Import validation tables;Import maestro graphs
339 | 7.4.1.3 | Orange | P&S Case Study - Check & Proofread |  | 2026-08-25 16:00 | 0% |  | IES;CS | 338FS | Series 3 IBA Development | Medium | Backlog | 2026-08-21 08:00 |  | 24 hours | 0 hours | 24 hours | 3 days | No
340 | 7.4.2 | Grey | Asset Health & Maintenance Case Study |  | 2026-09-18 16:00 | 0% |  |  |  |  | Medium |  | 2026-09-16 08:00 | 352FS | 24 hours | 0 hours | 24 hours | 3 days | No
341 | 7.4.2.1 | Orange | Maintenance Case Study - Share content with CS |  | 2026-09-16 16:00 | 0% |  | IES | 327FS | Series 3 IBA Development | Medium | Backlog | 2026-09-16 08:00 | 342FS | 8 hours | 0 hours | 8 hours | 1 day | No |  | 0/3 | receive CS approval;Update content;Share content
342 | 7.4.2.2 | Orange | Maintenance Case Study - Import |  | 2026-09-17 16:00 | 0% |  | IES | 341FS | Series 3 IBA Development | Medium | Backlog | 2026-09-17 08:00 | 343FS | 8 hours | 0 hours | 8 hours | 1 day | No |  | 0/3 | Import maestro content;Import validation tables;Import maestro graphs
343 | 7.4.2.3 | Orange | Maintenance Case Study - Check & Proofread |  | 2026-09-18 16:00 | 0% |  | IES;CS | 342FS | Series 3 IBA Development | Medium | Backlog | 2026-09-18 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No
344 | 7.4.3 | Grey | Plant Resource Efficiency Case Study |  | 2026-09-18 16:00 | 0% |  |  |  |  | Medium |  | 2026-09-16 08:00 | 354FS | 24 hours | 0 hours | 24 hours | 3 days | No
345 | 7.4.3.1 | Orange | RE Case Study - Share content with CS |  | 2026-09-16 16:00 | 0% |  | IES | 331FS | Series 3 IBA Development | Medium | Backlog | 2026-09-16 08:00 | 346FS | 8 hours | 0 hours | 8 hours | 1 day | No |  | 0/3 | Receive CS approval;update content;Share content
346 | 7.4.3.2 | Orange | RE Case Study - Import |  | 2026-09-17 16:00 | 0% |  | IES | 345FS | Series 3 IBA Development | Medium | Backlog | 2026-09-17 08:00 | 347FS | 8 hours | 0 hours | 8 hours | 1 day | No |  | 0/3 | Import maestro content;Import validation tables;Import maestro graphs
347 | 7.4.3.3 | Orange | RE Case Study - Check & Proofread |  | 2026-09-18 16:00 | 0% |  | IES;CS | 346FS | Series 3 IBA Development | Medium | Backlog | 2026-09-18 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No
348 | 7.5 | Black | Executive Review of IBA Results |  | 2026-09-21 16:00 | 0% |  |  |  |  | Medium |  | 2026-08-26 08:00 | 367FS | 56 hours | 0 hours | 56 hours | 19 days | No
349 | 7.5.1 | Grey | Planning & Scheduling IBA Review |  | 2026-09-01 16:00 | 0% |  |  |  |  | Medium |  | 2026-08-26 08:00 |  | 40 hours | 0 hours | 40 hours | 5 days | No
350 | 7.5.1.1 | Orange | P&S - Exec approval of financial benefit |  | 2026-09-01 16:00 | 0% |  | BD;CS;Exec;IES | 336FS | Series 3 IBA Development | Medium | Backlog | 2026-08-26 08:00 | 357FS, 358FS | 40 hours | 0 hours | 40 hours | 5 days | No |  |  |  | Complete POV
351 | 7.5.2 | Grey | Asset Health & Maintenance IBA Review |  | 2026-09-21 16:00 | 0% |  |  |  |  | Medium |  | 2026-09-21 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No
352 | 7.5.2.1 | Orange | Maintenance - Exec approval of financial benefit |  | 2026-09-21 16:00 | 0% |  | BD;CS;Exec;IES | 340FS | Series 3 IBA Development | Medium | Backlog | 2026-09-21 08:00 | 360FS, 361FS | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Complete POV
353 | 7.5.3 | Grey | Plant Resource Efficiency IBA Review |  | 2026-09-21 16:00 | 0% |  |  |  |  | Medium |  | 2026-09-21 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No
354 | 7.5.3.1 | Orange | RE - Exec approval of financial benefit |  | 2026-09-21 16:00 | 0% |  | BD;CS;Exec;IES | 344FS | Series 3 IBA Development | Medium | Backlog | 2026-09-21 08:00 | 363FS, 364FS | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Complete POV
355 | 7.6 | Black | Develop IBA Deck |  | 2026-09-24 16:00 | 0% |  |  |  |  | Medium |  | 2026-09-02 08:00 |  | 80 hours | 0 hours | 80 hours | 17 days | No
356 | 7.6.1 | Grey | Planning & Scheduling IBA Deck |  | 2026-09-04 16:00 | 0% |  |  |  |  | Medium |  | 2026-09-02 08:00 | 365FS | 48 hours | 0 hours | 48 hours | 3 days | No
357 | 7.6.1.1 | Orange | P&S - Develop design framework |  | 2026-09-04 16:00 | 0% |  | CS;Design | 350FS | Series 3 IBA Development | Medium | Backlog | 2026-09-02 08:00 |  | 24 hours | 0 hours | 24 hours | 3 days | No
358 | 7.6.1.2 | Orange | P&S - Develop storyboard |  | 2026-09-04 16:00 | 0% |  | CS;Design | 350FS | Series 3 IBA Development | Medium | Backlog | 2026-09-02 08:00 |  | 24 hours | 0 hours | 24 hours | 3 days | No
359 | 7.6.2 | Grey | Asset Health & Maintenance IBA Deck |  | 2026-09-22 16:00 | 0% |  |  |  |  | Medium |  | 2026-09-22 08:00 | 365FS | 16 hours | 0 hours | 16 hours | 1 day | No
360 | 7.6.2.1 | Orange | Maintenance - Develop design framework |  | 2026-09-22 16:00 | 0% |  | CS;Design | 352FS | Series 3 IBA Development | Medium | Backlog | 2026-09-22 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No
361 | 7.6.2.2 | Orange | Maintenance - Develop storyboard |  | 2026-09-22 16:00 | 0% |  | CS;Design | 352FS | Series 3 IBA Development | Medium | Backlog | 2026-09-22 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No
362 | 7.6.3 | Grey | Plant Resource Efficiency IBA Deck |  | 2026-09-22 16:00 | 0% |  |  |  |  | Medium |  | 2026-09-22 08:00 | 365FS | 16 hours | 0 hours | 16 hours | 1 day | No
363 | 7.6.3.1 | Orange | RE Deck - Develop design framework |  | 2026-09-22 16:00 | 0% |  | CS;Design | 354FS | Series 3 IBA Development | Medium | Backlog | 2026-09-22 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No
364 | 7.6.3.2 | Orange | RE Deck - Develop storyboard |  | 2026-09-22 16:00 | 0% |  | CS;Design | 354FS | Series 3 IBA Development | Medium | Backlog | 2026-09-22 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No
365 | 7.6.4 | Orange | Series 3 - Complete IBA Deck |  | 2026-09-23 16:00 | 0% |  | IES;CS | 356FS, 359FS, 362FS | Pre-Kick Off Planning | Medium | Backlog | 2026-09-23 08:00 | 366FS |  |  |  | 1 day | No
366 | 7.6.5 | Orange | Series 3 - IBA Deck - Executive Review |  | 2026-09-24 16:00 | 0% |  | Exec | 365FS | Pre-Kick Off Planning | Medium | Backlog | 2026-09-24 08:00 |  |  |  |  | 1 day | No |  |  |  | Complete POV
367 | 7.6.6 | Orange | Series 3 - POV Portal - Executive Review |  | 2026-09-22 16:00 | 0% |  | Exec | 348FS | Pre-Kick Off Planning | Medium | Backlog | 2026-09-22 08:00 |  |  |  |  | 1 day | No |  |  |  | Complete POV
368 | 8 | Black Outline | Go Live Deployment |  | 2026-12-31 17:00 | 0% |  |  | 282FS |  | Medium |  | 2026-09-25 08:00 | 430FS | 1288 hours | 0 hours | 1288 hours | 70 days | No
369 | 8.1 | Black | Live Data Integration |  | 2026-10-09 16:00 | 0% |  |  |  |  | Medium |  | 2026-09-25 08:00 |  | 224 hours | 0 hours | 224 hours | 11 days | No
370 | 8.1.1 | Orange | Finalize list of data sources |  | 2026-09-28 16:00 | 0% |  | BD;CS;Exec;IES;SCIE |  | Go Live Deployment | Medium | Backlog | 2026-09-25 08:00 | 396FS, 371FS | 16 hours | 0 hours | 16 hours | 2 days | No | Finalise list of all data sources for Live Test
371 | 8.1.2 | Orange | Find integration solution |  | 2026-09-29 16:00 | 0% |  | SCIE | 370FS | Go Live Deployment | Medium | Backlog | 2026-09-29 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No
372 | 8.1.3 | Orange | Confirm IT architecture |  | 2026-09-25 16:00 | 0% |  | IT;SCIE | 40FS | Go Live Deployment | Medium | Backlog | 2026-09-25 08:00 | 373FS, 386FS | 8 hours | 0 hours | 8 hours | 1 day | No |  | 0/4 | Confirm GWS arrangement;Confirm GWS type;Confirm IT architecture;Arrange call between IT teams
373 | 8.1.4 | Orange | Finalize IT Architecture |  | 2026-10-09 16:00 | 0% |  | IT;SCIE | 372FS | Go Live Deployment | Medium | Backlog | 2026-09-28 08:00 |  | 80 hours | 0 hours | 80 hours | 10 days | No |  | 0/2 | Save IT architecture to OneDrive;Update if necessary
374 | 8.1.5 | Orange | Deploy Gateway Server |  | 2026-09-25 16:00 | 0% |  | SCIE |  | Go Live Deployment | Medium | Backlog | 2026-09-25 08:00 | 375FS, 377FS | 8 hours | 0 hours | 8 hours | 1 day | No | Install all necessary software |  |  | Go Live Deployment
375 | 8.1.6 | Orange | Outbound Connection to Maestro |  | 2026-09-28 16:00 | 0% |  | SCIE;IT | 374FS | Go Live Deployment | Medium | Backlog | 2026-09-28 08:00 | 395FS | 8 hours | 0 hours | 8 hours | 1 day | No
376 | 8.1.7 | Orange | Client prepare environment |  |  | 0% |  | SCIE |  | Go Live Deployment | Medium | Backlog | [6 empty] | No | Make ethernet connections, provide office space for gateway server etc.
377 | 8.1.8 | Orange | Make Live Connection |  | 2026-09-28 16:00 | 0% |  | SCIE | 374FS | Go Live Deployment | Medium | Backlog | 2026-09-28 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No
378 | 8.1.9 | Orange | Validate Live Data Connection |  | 2026-09-25 16:00 | 0% |  | IES;SCIE;IT |  | Go Live Deployment | Medium | Backlog | 2026-09-25 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Go Live Deployment
379 | 8.1.10 | Orange | Test VPN Connection |  |  | 0% |  | SCIE;IT |  | Go Live Deployment | Medium | Backlog | [6 empty] | No
380 | 8.1.11 | Orange | CM to M or Push Data to Maestro |  | 2026-10-08 16:00 | 0% |  | R&D;SCIE |  | Go Live Deployment | Medium | Backlog | 2026-09-25 08:00 |  | 80 hours | 0 hours | 80 hours | 10 days | No | Use CM to M or any other script to push data
381 | 8.2 | Black | Configure Maestro Performance Center |  | 2026-11-11 17:00 | 0% |  |  |  |  | Medium |  | 2026-09-25 08:00 | 392FS | 272 hours | 0 hours | 272 hours | 34 days | No
382 | 8.2.1 | Orange | Generate KPI list |  | 2026-10-05 16:00 | 0% |  | IES |  | Go Live Deployment | Medium | Backlog | 2026-09-25 08:00 | 383FS | 56 hours | 0 hours | 56 hours | 7 days | No | generate a list of vertical-specific/client-used KPIs
383 | 8.2.2 | Orange | Build KPI formulas |  | 2026-10-14 16:00 | 0% |  | IES | 382FS | Go Live Deployment | Medium | Backlog | 2026-10-06 08:00 | 384FS | 56 hours | 0 hours | 56 hours | 7 days | No | Use tag/datapoint list to build out KPI formula
384 | 8.2.3 | Orange | KT w/DS for KPIs to be produced |  | 2026-10-15 16:00 | 0% |  | IES | 383FS | Go Live Deployment | Medium | Backlog | 2026-10-15 08:00 | 385FS | 8 hours | 0 hours | 8 hours | 1 day | No
385 | 8.2.4 | Orange | Create initial KPI output values |  | 2026-10-20 16:00 | 0% |  | DS | 384FS | Go Live Deployment | Medium | Backlog | 2026-10-16 08:00 | 386FS | 24 hours | 0 hours | 24 hours | 3 days | No | Create initial KPI output values for validation
386 | 8.2.5 | Orange | Validate KPI output values |  | 2026-10-23 16:00 | 0% |  | IES | 385FS, 372FS | Go Live Deployment | Medium | Backlog | 2026-10-21 08:00 | 387FS, 388FS | 24 hours | 0 hours | 24 hours | 3 days | No
387 | 8.2.6 | Orange | Provide 'when not to display' rule |  | 2026-10-26 16:00 | 0% |  | DS | 386FS | Go Live Deployment | Medium | Backlog | 2026-10-26 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | If some data is missing or values are out of range provide a 'when not to display rule'
388 | 8.2.7 | Orange | Modify KPI formulas where possible |  | 2026-10-30 16:00 | 0% |  | IES | 386FS | Go Live Deployment | Medium | Backlog | 2026-10-26 08:00 | 389FS | 40 hours | 0 hours | 40 hours | 5 days | No
389 | 8.2.8 | Orange | Build out KPI list in maestro |  | 2026-11-10 17:00 | 0% |  | R&D | 388FS | Go Live Deployment | Medium | Backlog | 2026-11-02 09:00 | 394FS, 390FS | 56 hours | 0 hours | 56 hours | 7 days | No | Build out KPI list in maestro, with object locations for DS scripts to push data | 0/2 | Output KPI by using correct Object & Property ID;Import Mapper file from R&D
390 | 8.2.9 | Orange | Executive review of Performance Center |  | 2026-11-11 17:00 | 0% |  | Exec | 389FS | Go Live Deployment | Medium | Backlog | 2026-11-11 09:00 |  |  |  |  | 1 day | No |  |  |  | Go Live Deployment
391 | 8.3 | Black | Live Test Model Transition |  | 2026-12-25 17:00 | 0% |  |  |  |  | Medium |  | 2026-09-29 08:00 | 402FS | 424 hours | 0 hours | 424 hours | 64 days | No
392 | 8.3.1 | Orange | Create fault tolerance mechanisms |  | 2026-11-16 17:00 | 0% |  | IES;R&D | 381FS | Go Live Deployment | Medium | Backlog | 2026-11-12 09:00 | 393FS | 24 hours | 0 hours | 24 hours | 3 days | No | For each model and data source, create a fault tolerance mechanism for the directive. Ensure that directives do not appear when data does not make sense.
393 | 8.3.2 | Orange | Test fault tolerance mechanism |  | 2026-11-30 17:00 | 0% |  | IES | 392FS | Go Live Deployment | Medium | Backlog | 2026-11-17 09:00 |  | 80 hours | 0 hours | 80 hours | 10 days | No | Test fault tolerance methods
394 | 8.3.3 | Orange | Update bound & changing rates |  | 2026-11-12 17:00 | 0% |  | IES;DS | 389FS | Go Live Deployment | Medium | Backlog | 2026-11-11 09:00 | 397FS | 16 hours | 0 hours | 16 hours | 2 days | No | For each directive update bounds and minimum/maximum changing rates. Have DS implement these for directives | 0/5 | Implement bounds & rates into live deployment;Share bounds & rates with DS;Create maximum changing rates;Create minimum changing rates;Create bounds for each directive
395 | 8.3.4 | Orange | Confirm manual data sharing methods and locations |  | 2026-10-01 16:00 | 0% |  | SCIE;IES | 375FS | Go Live Deployment | Medium | Backlog | 2026-09-29 08:00 |  | 24 hours | 0 hours | 24 hours | 3 days | No | Depends on internet connection
396 | 8.3.5 | Orange | Confirm receipt of data |  | 2026-10-02 16:00 | 0% |  | IES;DS | 370FS | Go Live Deployment | Medium | Backlog | 2026-09-29 08:00 | 397FS | 32 hours | 0 hours | 32 hours | 4 days | No | Confirm reciept of data in the live environment and pass these to DS | 0/1 | Test query on live server to ensure data
397 | 8.3.6 | Orange | Publish Model |  | 2026-12-02 17:00 | 0% |  | DS | 396FS, 394FS | Go Live Deployment | Medium | Backlog | 2026-11-13 09:00 | 398FS | 112 hours | 0 hours | 112 hours | 14 days | No | Publish model in Maestro | 0/2 | Test the deployment envrionment;Package everything and deploy on the server
398 | 8.3.7 | Orange | Create test period for directive issuance |  | 2026-12-03 17:00 | 0% |  | R&D | 397FS | Go Live Deployment | Medium | Backlog | 2026-12-03 09:00 | 399FS | 8 hours | 0 hours | 8 hours | 1 day | No
399 | 8.3.8 | Orange | Update directive issuance |  | 2026-12-10 17:00 | 0% |  | R&D | 398FS | Go Live Deployment | Medium | Backlog | 2026-12-04 09:00 | 400FS | 40 hours | 0 hours | 40 hours | 5 days | No | Update the directive issuance in line with the fault tolerance
400 | 8.3.9 | Orange | Update Models |  | 2026-12-24 17:00 | 0% |  | DS | 399FS | Go Live Deployment | Medium | Backlog | 2026-12-11 09:00 | 401FS | 80 hours | 0 hours | 80 hours | 10 days | No | Update the models to include the fault tolerance methods | 0/1 | Ad-hoc
401 | 8.3.10 | Orange | Finalize and Deploy Live Test Models |  | 2026-12-25 17:00 | 0% |  | IES;R&D;DS | 400FS | Go Live Deployment | Medium | Backlog | 2026-12-25 09:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Go Live Deployment
402 | 8.4 | Black | Go Live Governance |  | 2026-12-31 17:00 | 0% |  |  | 391FS |  | Medium |  | 2026-12-28 09:00 |  | 56 hours | 0 hours | 56 hours | 4 days | No
403 | 8.4.1 | Orange | Set client weekly meeting time |  | 2026-12-28 17:00 | 0% |  | BD;CS;Exec;IES;SCIE |  | Go Live Deployment | Medium | Backlog | 2026-12-28 09:00 | 405FS, 404FS | 8 hours | 0 hours | 8 hours | 1 day | No
404 | 8.4.2 | Orange | Hold first weekly client meeting |  | 2026-12-29 17:00 | 0% |  | IES;CS;BD | 403FS | Go Live Deployment | Medium | Backlog | 2026-12-29 09:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Go Live Deployment
405 | 8.4.3 | Orange | Publish Live Test Status Update |  | 2026-12-29 17:00 | 0% |  | BD;CS;Exec;IES | 403FS | Go Live Deployment | Medium | Backlog | 2026-12-29 09:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | Review and publish first Live Test Status Update, and set up ongoing template | 0/3 | Set up ongoing template;Publish Live Test Status Update;Review Live Test Status Update
406 | 8.4.4 | Orange | Determine what access LYB employees will have |  | 2026-12-28 17:00 | 0% |  | CS;BD;Exec |  | Go Live Deployment | Medium | Backlog | 2026-12-28 09:00 | 407FS | 8 hours | 0 hours | 8 hours | 1 day | No
407 | 8.4.5 | Orange | Grant limited access |  | 2026-12-29 17:00 | 0% |  | R&D | 406FS | Go Live Deployment | Medium | Backlog | 2026-12-29 09:00 | 408FS | 8 hours | 0 hours | 8 hours | 1 day | No
408 | 8.4.6 | Orange | Meet with LYB to explain functionality |  | 2026-12-30 17:00 | 0% |  | BD;CS;Exec;IES | 407FS | Go Live Deployment | Medium | Backlog | 2026-12-30 09:00 | 409FS | 8 hours | 0 hours | 8 hours | 1 day | No
409 | 8.4.7 | Orange | Commence directive implementation |  | 2026-12-31 17:00 | 0% |  | IES | 408FS | Go Live Deployment | Medium | Backlog | 2026-12-31 09:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No |  |  |  | Go Live Deployment
410 | 8.5 | Black | Implementation Control |  | 2026-11-05 17:00 | 0% |  |  |  |  | Medium |  | 2026-09-25 08:00 |  | 312 hours | 0 hours | 312 hours | 30 days | No
411 | 8.5.1 | Grey | Series 1 |  | 2026-10-08 16:00 | 0% |  |  |  |  | Medium |  | 2026-09-25 08:00 | 417FS, 431FS, 429FS | 104 hours | 0 hours | 104 hours | 10 days | No
412 | 8.5.1.1 | Orange | Expedite Maestro control |  | 2026-09-25 16:00 | 0% |  | SCIE;IES |  | Go Live Deployment | Medium | Backlog | 2026-09-25 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | Work with automation/control department to expedite Maestro control
413 | 8.5.1.2 | Orange | Develop implementation detection |  | 2026-10-01 16:00 | 0% |  | R&D |  | Go Live Deployment | Medium | Backlog | 2026-09-25 08:00 | 415FS | 40 hours | 0 hours | 40 hours | 5 days | No | For each model, use R&D to develop an implementation detection (monitor if changes match directive)
414 | 8.5.1.3 | Orange | Create known route to implementation |  | 2026-09-25 16:00 | 0% |  | R&D |  | Go Live Deployment | Medium | Backlog | 2026-09-25 08:00 | 415FS | 8 hours | 0 hours | 8 hours | 1 day | No | Create a known root to implementation for each directive. Determine if directive will be advisory or implemented. If advisory set up advisory implementation path – how we will move this from advisory to automated. Create path for advisory mode directives. Deliver automated. | 0/3 | Create advisory to automated path;set up advisory implementation path;Determine if directive will be advisory or implemented
415 | 8.5.1.4 | Orange | Create implementation report outline |  | 2026-10-08 16:00 | 0% |  | IES;R&D | 414FS, 413FS | Go Live Deployment | Medium | Backlog | 2026-10-02 08:00 |  | 40 hours | 0 hours | 40 hours | 5 days | No | Create outline for reporting out to client implementation rates
416 | 8.5.1.5 | Orange | Revisit Automated Control |  | 2026-09-25 16:00 | 0% |  | IES |  | Go Live Deployment | Medium | Backlog | 2026-09-25 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | After a period of implementation revists implementing some maestro directives automatically
417 | 8.5.2 | Grey | Series 2 |  | 2026-10-22 16:00 | 0% |  |  | 411FS |  | Medium |  | 2026-10-09 08:00 | 423FS | 104 hours | 0 hours | 104 hours | 10 days | No
418 | 8.5.2.1 | Orange | Expedite Maestro control |  | 2026-10-09 16:00 | 0% |  | SCIE;IES |  | Go Live Deployment | Medium | Backlog | 2026-10-09 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | Work with automation/control department to expedite Maestro control
419 | 8.5.2.2 | Orange | Develop implementation detection |  | 2026-10-15 16:00 | 0% |  | R&D |  | Go Live Deployment | Medium | Backlog | 2026-10-09 08:00 | 421FS | 40 hours | 0 hours | 40 hours | 5 days | No | For each model, use R&D to develop an implementation detection (monitor if changes match directive)
420 | 8.5.2.3 | Orange | Create known route to implementation |  | 2026-10-09 16:00 | 0% |  | R&D |  | Go Live Deployment | Medium | Backlog | 2026-10-09 08:00 | 421FS | 8 hours | 0 hours | 8 hours | 1 day | No | Create a known route to implementation for each directive | 0/3 | Create advisory to automated path;Set up advisory implementation path;Determine if directive will be advisory or implemented
421 | 8.5.2.4 | Orange | Create implementation report outline |  | 2026-10-22 16:00 | 0% |  | IES;R&D | 420FS, 419FS | Go Live Deployment | Medium | Backlog | 2026-10-16 08:00 |  | 40 hours | 0 hours | 40 hours | 5 days | No | Create outline for reporting out to client implementation rates
422 | 8.5.2.5 | Orange | Revisit Automated Control |  | 2026-10-09 16:00 | 0% |  | IES |  | Go Live Deployment | Medium | Backlog | 2026-10-09 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | After a period of implementation revists implementing some maestro directives automatically
423 | 8.5.3 | Grey | Series 3 |  | 2026-11-05 17:00 | 0% |  |  | 417FS |  | Medium |  | 2026-10-23 08:00 |  | 104 hours | 0 hours | 104 hours | 10 days | No
424 | 8.5.3.1 | Orange | Expedite Maestro control |  | 2026-10-23 16:00 | 0% |  | SCIE;IES |  | Go Live Deployment | Medium | Backlog | 2026-10-23 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | Work with automation/control department to expedite Maestro control
425 | 8.5.3.2 | Orange | Develop implementation detection |  | 2026-10-29 16:00 | 0% |  | R&D |  | Go Live Deployment | Medium | Backlog | 2026-10-23 08:00 | 427FS | 40 hours | 0 hours | 40 hours | 5 days | No | For each model, use R&D to develop an implementation detection (monitor if changes match directive)
426 | 8.5.3.3 | Orange | Create known route to implementation |  | 2026-10-23 16:00 | 0% |  | R&D |  | Go Live Deployment | Medium | Backlog | 2026-10-23 08:00 | 427FS | 8 hours | 0 hours | 8 hours | 1 day | No | Create a known root to implementation for each directive | 0/3 | Create advisory to automated path;Set up advisory implementation path;Determine if directive will be advisory or implemented
427 | 8.5.3.4 | Orange | Create implementation report outline |  | 2026-11-05 17:00 | 0% |  | IES;R&D | 426FS, 425FS | Go Live Deployment | Medium | Backlog | 2026-10-30 08:00 |  | 40 hours | 0 hours | 40 hours | 5 days | No | Create outline for reporting out to client implementation rates
428 | 8.5.3.5 | Orange | Revisit Automated Control |  | 2026-10-23 16:00 | 0% |  | IES |  | Go Live Deployment | Medium | Backlog | 2026-10-23 08:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No | After a period of implementation revists implementing some maestro directives automatically
429 | 8.5.4 | Orange | Review first implementation report |  | 2026-10-09 16:00 | 0% |  | IES;CS;BD;Exec | 411FS | Go Live Deployment | Medium | Backlog | 2026-10-09 08:00 |  |  |  |  | 1 day | No |  |  |  | Go Live Deployment
430 | 9 | Black Outline | Ongoing Delivery |  | 2027-02-05 17:00 | 0% |  |  | 368FS |  | Medium |  | 2027-01-01 09:00 |  | 360 hours | 0 hours | 360 hours | 26 days | No
431 | 9.1 | Grey | Client Workstream Owner Introductions |  | 2027-01-20 17:00 | 0% |  |  | 411FS |  | Medium |  | 2027-01-01 09:00 | 434FS | 224 hours | 0 hours | 224 hours | 14 days | No
432 | 9.1.1 | Orange | Client Services |  | 2027-01-20 17:00 | 0% |  | BD;CS;Exec;IES |  | Ongoing Delivery | Medium | Backlog | 2027-01-01 09:00 |  | 112 hours | 0 hours | 112 hours | 14 days | No | Providing updates to clients
433 | 9.1.2 | Orange | Introductions to client owners for each workstream |  | 2027-01-20 17:00 | 0% |  | BD;CS;Exec;IES |  | Ongoing Delivery | Medium | Backlog | 2027-01-01 09:00 |  | 112 hours | 0 hours | 112 hours | 14 days | No
434 | 9.2 | Grey | Internal Weekly Call |  | 2027-01-21 17:00 | 0% |  |  | 431FS |  | Medium |  | 2027-01-21 09:00 | 437FS | 16 hours | 0 hours | 16 hours | 1 day | No
435 | 9.2.1 | Orange | Set Internal Weekly Call |  | 2027-01-21 17:00 | 0% |  | IES;CS;DS |  | Ongoing Delivery | Medium | Backlog | 2027-01-21 09:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No |  | 0/3 | Publish meeting minutes;Monitor incoming data source connections;Monitor/track directive implementation & generation
436 | 9.2.2 | Orange | Ensure correct audience Internal Weekly Call |  | 2027-01-21 17:00 | 0% |  | IES;CS |  | Ongoing Delivery | Medium | Backlog | 2027-01-21 09:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No
437 | 9.3 | Grey | Weekly Client Call |  | 2027-01-22 17:00 | 0% |  |  | 434FS |  | Medium |  | 2027-01-22 09:00 | 440FS | 16 hours | 0 hours | 16 hours | 1 day | No
438 | 9.3.1 | Orange | Set Weekly Client Call |  | 2027-01-22 17:00 | 0% |  | IES;CS;DS |  | Ongoing Delivery | Medium | Backlog | 2027-01-22 09:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No |  | 0/4 | Publish meeting minutes;Review status update actions;Publish live test statu update;Forward Status Update
439 | 9.3.2 | Orange | Ensure correct audience Weekly Client Call |  | 2027-01-22 17:00 | 0% |  | CS |  | Ongoing Delivery | Medium | Backlog | 2027-01-22 09:00 |  | 8 hours | 0 hours | 8 hours | 1 day | No
440 | 9.4 | Grey | Reporting |  | 2027-02-05 17:00 | 0% |  |  | 437FS |  | Medium |  | 2027-01-25 09:00 |  | 104 hours | 0 hours | 104 hours | 10 days | No
441 | 9.4.1 | Orange | Publish Executive Report every month |  | 2027-02-05 17:00 | 0% |  | CS;IES |  | Ongoing Delivery | Medium | Backlog | 2027-01-25 09:00 |  | 80 hours | 0 hours | 80 hours | 10 days | No
442 | 9.4.2 | Orange | Issue Weekly Live Test Updates |  | 2027-01-27 17:00 | 0% |  | CS;IES |  | Ongoing Delivery | Medium | Backlog | 2027-01-25 09:00 |  | 24 hours | 0 hours | 24 hours | 3 days | No | Issue Weekly Live Test Updates (to client and forward internally)

## Gantt Chart Table & Instruction
Tasks | Start Date | Completion | Length | Steps
Pre-Kick Off Plan | 2025-06-02 08:00 | 2025-10-08 16:00 | 128.3333 | 1 | Set up as shown in table to the right
Client Onboarding | 2025-06-02 08:00 | 2025-07-04 16:00 | 32.3333 | 2 | Click on start date and change to the general format
Review Existing Case Studies | 2025-06-02 08:00 | 2025-06-20 16:00 | 18.3333 | 3 | Create gantt chart with Start Date and Length (total days to complete)
List Initial Target Benefit Ideas | 2025-06-23 08:00 | 2025-07-04 16:00 | 11.3333 | 4 | Click on Insert → recommended charts → all charts → bar → stacked bar → press okay to insert
Set Up project On MS Cloud | 2025-06-02 08:00 | 2025-06-16 16:00 | 14.3333 | 5 | Dates at the bottom will show up as the numbers (from chaning to general format)
Develop Scope | 2025-06-02 08:00 | 2025-09-18 16:00 | 108.3333 | 6 | Highlight start date cells and change them back to date format
Preparation | 2025-06-02 08:00 | 2025-06-27 16:00 | 25.3333 | 7 | Format the data series that coincides with the "Start Date", make this have no fill & no line
Research & Review Client Process | 2025-06-02 08:00 | 2025-06-27 16:00 | 25.3333 | 8 | Change start point on X axis to be close to where the stack series begins
Determine most viable sites | 2025-06-20 08:00 | 2025-06-26 16:00 | 6.3333 | 9 | Double click on task list to format → axis options → check cateogires in reverse order
Determine Use Cases | 2025-07-21 08:00 | 2025-08-01 16:00 | 11.3333 | 10 | For more clarity keep only the heading titles as bold
Profit & Loss (P&L) | 2025-08-04 08:00 | 2025-08-28 16:00 | 24.3333
P&L - 1st Draft | 2025-08-04 08:00 | 2025-08-13 16:00 | 9.3333
P&L - Review | 2025-08-14 08:00 | 2025-08-27 16:00 | 13.3333
P&L - Value Optimization Analysis | 2025-08-28 08:00 | 2025-08-28 16:00 | 0.33333
P&L - Finalized | 2025-08-28 08:00 | 2025-08-28 16:00 | 0.33333
Statement of Work (SOW) | 2025-08-04 08:00 | 2025-09-03 16:00 | 30.3333
SOW - 1st Draft | 2025-08-04 08:00 | 2025-08-21 16:00 | 17.3333
SOW - Review Draft with CS | 2025-08-22 08:00 | 2025-08-27 16:00 | 5.3333
SOW - Format & Update Design Elements | 2025-08-28 08:00 | 2025-08-29 16:00 | 1.3333
SOW - Confirm Indicative IT Architecture | 2025-08-28 08:00 | 2025-08-29 16:00 | 1.3333
SOW - Finalized | 2025-09-01 08:00 | 2025-09-03 16:00 | 2.3333
Create DRT | 2025-06-20 08:00 | 2025-09-10 16:00 | 82.3333
DRT - 1st Draft | 2025-06-20 08:00 | 2025-06-20 16:00 | 0.33333
DRT - Review | 2025-09-04 08:00 | 2025-09-08 16:00 | 4.3333
Develop Data Source System Roadmap | 2025-09-09 08:00 | 2025-09-10 16:00 | 1.3333
DRT - Finalized | 2025-09-09 08:00 | 2025-09-09 16:00 | 0.33333
Executive Presentation (EP) | 2025-08-04 08:00 | 2025-09-18 16:00 | 45.3333
EP - 1st Draft | 2025-08-04 08:00 | 2025-08-11 16:00 | 7.3333
EP - Review Draft with CS | 2025-09-04 08:00 | 2025-09-10 16:00 | 6.3333
EP - Update Design Elements | 2025-09-11 08:00 | 2025-09-11 16:00 | 0.33333
EP - Final Draft | 2025-09-12 08:00 | 2025-09-18 16:00 | 6.3333
Initiate Benefit Measurement Workstream | 2025-08-07 08:00 | 2025-10-08 16:00 | 62.3333
Arrange briefing call with EPA | 2025-08-07 08:00 | 2025-08-07 16:00 | 0.33333
Outline rough case studies | 2025-09-02 08:00 | 2025-09-10 16:00 | 8.3333
Begin drafting BCMS using previous examples | 2025-09-02 08:00 | 2025-09-04 16:00 | 2.3333
Work with Legal team to draft the final BCMs | 2025-09-05 08:00 | 2025-09-15 16:00 | 10.3333
Liaise with Legal to Complete Drafts | 2025-09-05 08:00 | 2025-10-08 16:00 | 33.3333
IT Architecture Discussion | 2025-07-31 08:00 | 2025-09-25 16:00 | 56.3333
Arrange call with Sam Babler, if required | 2025-07-31 08:00 | 2025-07-31 16:00 | 0.33333
Prepare IT Architecture Diagram | 2025-09-01 08:00 | 2025-09-05 16:00 | 4.3333
Publish IT Architecture diagram to Client | 2025-09-10 08:00 | 2025-09-25 16:00 | 15.3333
External POV and Live Test Preview Call | 2025-09-04 08:00 | 2025-09-25 16:00 | 21.3333
Submit Security Questionnaire | 2025-09-04 08:00 | 2025-09-04 16:00 | 0.33333
Security Questionnaire - Client Approval | 2025-09-10 08:00 | 2025-09-25 16:00 | 15.3333
Create Kick-Off Planning Presentation | 2025-09-12 08:00 | 2025-09-23 16:00 | 11.3333
Update Kick-Off Presentation Design Elements | 2025-09-24 08:00 | 2025-09-25 16:00 | 1.3333
Confirm Kick-Off Meeting Date | 2025-09-24 08:00 | 2025-09-24 16:00 | 0.33333
POV Kick-Off | 2025-09-24 08:00 | 2025-12-19 17:00 | 86.375
External Kick-Off Meeting | 2025-10-28 08:00 | 2025-12-10 17:00 | 43.375
Hold External Kick-off Meeting | 2025-10-28 08:00 | 2025-10-28 16:00 | 0.33333
Confirm data sharing method and location | 2025-10-29 08:00 | 2025-10-29 16:00 | 0.33333
Identify server resources | 2025-10-29 08:00 | 2025-10-29 16:00 | 0.33333
Ensure Elutions equipment is ready | 2025-10-30 08:00 | 2025-10-30 16:00 | 0.33333
Review DRT with client | 2025-10-29 08:00 | 2025-12-10 17:00 | 42.375
Confirm client weekly meeting time | 2025-10-29 08:00 | 2025-10-29 16:00 | 0.33333
POV status Update | 2025-10-29 08:00 | 2025-11-04 17:00 | 6.375
Maestro Demo for wider project team (Optional) | 2025-10-29 08:00 | 2025-10-29 16:00 | 0.33333
Kick-Off Call Internal Washup | 2025-10-29 08:00 | 2025-10-30 16:00 | 1.3333
Review Meeting Actions with Elutions team | 2025-10-29 08:00 | 2025-10-29 16:00 | 0.33333
Schedule placeholder for internal weekly calls | 2025-10-30 08:00 | 2025-10-30 16:00 | 0.33333
Client Workstream Owner Introductions | 2025-12-11 09:00 | 2025-12-19 17:00 | 8.3333
Introductions to client systems and IT resource | 2025-12-11 09:00 | 2025-12-17 17:00 | 6.3333
Send Integration Questionaire to Client | 2025-12-18 09:00 | 2025-12-18 17:00 | 0.33333
Receive and Review Integration Questionaire | 2025-12-19 09:00 | 2025-12-19 17:00 | 0.33333
Request VPN Connection | 2025-12-18 09:00 | 2025-12-18 17:00 | 0.33333
Save contract details to OneNote | 2025-12-11 09:00 | 2025-12-11 17:00 | 0.33333
Introductions to client owners for each workstream | 2025-12-11 09:00 | 2025-12-17 17:00 | 6.3333
Data Science Preparation | 2025-09-25 08:00 | 2025-09-26 16:00 | 1.3333
KT w/ DS for use cases | 2025-09-25 08:00 | 2025-09-25 16:00 | 0.33333
Familiarize & Practice Modeling | 2025-09-26 08:00 | 2025-09-26 16:00 | 0.33333
POV Governance | 2025-09-24 08:00 | 2025-11-04 17:00 | 41.375
Internal Weekly Call | 2025-10-31 08:00 | 2025-10-31 16:00 | 0.33333
Publish Agenda | 2025-10-31 08:00 | 2025-10-31 16:00 | 0.33333
Confirm Attendees | 2025-10-31 08:00 | 2025-10-31 16:00 | 0.33333
Weekly Client Call | 2025-11-03 09:00 | 2025-11-04 17:00 | 1.3333
Publish Weekly Client Call Agenda | 2025-11-03 09:00 | 2025-11-03 17:00 | 0.33333
Confirm Weekly Client Call Attendees | 2025-11-04 09:00 | 2025-11-04 17:00 | 0.33333
Contractual Obligations | 2025-09-25 08:00 | 2025-10-09 16:00 | 14.3333
Share Contractual Obligations | 2025-10-09 08:00 | 2025-10-09 16:00 | 0.33333
Establish processes for ongoing contractual obligations | 2025-09-25 08:00 | 2025-10-09 16:00 | 14.3333
Establish Exec Review Framework | 2025-09-24 08:00 | 2025-10-10 16:00 | 16.3333
Create Planner Goals? | 2025-09-24 08:00 | 2025-10-10 16:00 | 16.3333
Data Collection & Benefit Measurement | 2025-12-11 09:00 | 2026-01-09 17:00 | 29.3333
Historical Data Collection | 2025-12-11 09:00 | 2026-01-09 17:00 | 29.3333
Data Collection | 2025-12-11 09:00 | 2026-01-01 17:00 | 21.3333
Complete historical data collection | 2026-01-02 09:00 | 2026-01-02 17:00 | 0.33333
Review of historical data | 2026-01-05 09:00 | 2026-01-05 17:00 | 0.33333
Creating scripts for historical data transfer | 2026-01-06 09:00 | 2026-01-09 17:00 | 3.3333
Store data in OneDrive | 2026-01-06 09:00 | 2026-01-06 17:00 | 0.33333
Update DRT with receipt of data | 2026-01-06 09:00 | 2026-01-06 17:00 | 0.33333
Portal Development | 2025-06-02 08:00 | 2026-01-05 17:00 | 217.375
Maestro Screen Design Document | 2025-09-19 08:00 | 2025-10-15 16:00 | 26.3333
Outline changes for existing Maestro screens | 2025-09-19 08:00 | 2025-09-23 16:00 | 4.3333
Create mock ups for existing screens | 2025-09-24 08:00 | 2025-10-07 16:00 | 13.3333
Mock up approval | 2025-10-08 08:00 | 2025-10-08 16:00 | 0.33333
Share Mock Ups to R&D | 2025-10-09 08:00 | 2025-10-09 16:00 | 0.33333
Outline where object trees are required | 2025-09-26 08:00 | 2025-10-15 16:00 | 19.3333
Provide import files where possible | 2025-09-19 08:00 | 2025-10-01 16:00 | 12.3333
Develop POV Portal | 2025-06-02 08:00 | 2026-01-05 17:00 | 217.375
IES Import POV Info | 2025-10-02 08:00 | 2025-10-13 16:00 | 11.3333
DS Import POV info | 2026-01-05 09:00 | 2026-01-05 17:00 | 0.33333
Develop new additional dashboards | 2025-10-16 08:00 | 2025-10-29 16:00 | 13.3333
Develop process centre | 2025-10-16 08:00 | 2025-11-04 17:00 | 19.375
Create trend viewer | 2025-06-02 08:00 | 2025-06-03 16:00 | 1.3333
Develop benefit centre | 2025-10-16 08:00 | 2025-11-04 17:00 | 19.375
Create object tree(s) | 2025-10-16 08:00 | 2025-10-16 16:00 | 0.33333
Develop impact centre | 2025-10-16 08:00 | 2025-11-04 17:00 | 19.375
Review existing dashboards for vertical | 2025-10-30 08:00 | 2025-10-30 16:00 | 0.33333
Complete development of POV portal | 2025-11-05 09:00 | 2025-11-05 17:00 | 0.33333
Series 1 IBA Development | 2026-01-12 09:00 | 2026-03-24 16:00 | 71.2917
Data Qualification | 2026-01-12 09:00 | 2026-01-19 17:00 | 7.3333
Steam Network Data Qualification | 2026-01-12 09:00 | 2026-01-19 17:00 | 7.3333
Steam Network - Establish Data Connection | 2026-01-12 09:00 | 2026-01-12 17:00 | 0.33333
Steam Network - Validate Data | 2026-01-13 09:00 | 2026-01-13 17:00 | 0.33333
Steam Network - Check Data Availability | 2026-01-14 09:00 | 2026-01-16 17:00 | 2.3333
Steam Network - Mark Receipt of Each Data Source | 2026-01-19 09:00 | 2026-01-19 17:00 | 0.33333
Fuel Balance Data Qualification | 2026-01-12 09:00 | 2026-01-19 17:00 | 7.3333
Fuel - Establish Data Connection | 2026-01-12 09:00 | 2026-01-12 17:00 | 0.33333
Fuel - Validate Data | 2026-01-13 09:00 | 2026-01-13 17:00 | 0.33333
Fuel - Check Data Availability | 2026-01-14 09:00 | 2026-01-16 17:00 | 2.3333
Fuel - Mark Receipt of Each Data Source | 2026-01-19 09:00 | 2026-01-19 17:00 | 0.33333
Production Yield Data Qualification | 2026-01-12 09:00 | 2026-01-19 17:00 | 7.3333
Yield - Establish Data Connection | 2026-01-12 09:00 | 2026-01-12 17:00 | 0.33333
Yield - Validate Data | 2026-01-13 09:00 | 2026-01-13 17:00 | 0.33333
Yield - Check Data Availability | 2026-01-14 09:00 | 2026-01-16 17:00 | 2.3333
Yield - Mark Receipt of Each Data Source | 2026-01-19 09:00 | 2026-01-19 17:00 | 0.33333
Digital Twin, Mapping and Prediction | 2026-01-20 09:00 | 2026-02-04 17:00 | 15.3333
Steam Network Digital Twin | 2026-01-20 09:00 | 2026-02-03 17:00 | 14.3333
Steam - Determine relevant tags & target | 2026-01-20 09:00 | 2026-01-22 17:00 | 2.3333
Steam - DS KT session | 2026-01-23 09:00 | 2026-01-23 17:00 | 0.33333
Steam - Label tags for the models | 2026-01-23 09:00 | 2026-01-27 17:00 | 4.3333
Steam - Create Bounds & Changing Rates | 2026-01-28 09:00 | 2026-01-28 17:00 | 0.33333
Steam - Generate model | 2026-01-29 09:00 | 2026-01-29 17:00 | 0.33333
Steam - Ensure correct formatting and that data is uploaded to Maestro | 2026-01-30 09:00 | 2026-02-03 17:00 | 4.3333
Fuel Balance Digital Twin | 2026-01-20 09:00 | 2026-02-03 17:00 | 14.3333
Fuel - Determine relevant tags & target | 2026-01-20 09:00 | 2026-01-22 17:00 | 2.3333
Fuel - DS KT session | 2026-01-23 09:00 | 2026-01-23 17:00 | 0.33333
Fuel - Label tags for the models | 2026-01-23 09:00 | 2026-01-27 17:00 | 4.3333
Fuel - Create Bounds & Changing Rates | 2026-01-28 09:00 | 2026-01-28 17:00 | 0.33333
Fuel - Generate model | 2026-01-29 09:00 | 2026-01-29 17:00 | 0.33333
Fuel - Ensure correct formatting and that data is uploaded to Maestro | 2026-01-30 09:00 | 2026-02-03 17:00 | 4.3333
Production Yield Digital Twin | 2026-01-20 09:00 | 2026-02-03 17:00 | 14.3333
Yield - Determine relevant tags & target | 2026-01-20 09:00 | 2026-01-22 17:00 | 2.3333
Yield - DS KT session | 2026-01-23 09:00 | 2026-01-23 17:00 | 0.33333
Yield - Label tags for the models | 2026-01-23 09:00 | 2026-01-27 17:00 | 4.3333
Yield - Create Bounds & Changing Rates | 2026-01-28 09:00 | 2026-01-28 17:00 | 0.33333
Yield - Generate model | 2026-01-29 09:00 | 2026-01-29 17:00 | 0.33333
Yield - Ensure correct formatting and that data is uploaded to Maestro | 2026-01-30 09:00 | 2026-02-03 17:00 | 4.3333
Stack Series Models | 2026-02-04 09:00 | 2026-02-04 17:00 | 0.33333
Benefit Quantification | 2026-01-30 09:00 | 2026-02-11 17:00 | 12.3333
Steam Network Benefit Quantification | 2026-01-30 09:00 | 2026-02-11 17:00 | 12.3333
Steam - Establish benefit measurement methodology | 2026-01-30 09:00 | 2026-02-03 17:00 | 4.3333
Steam - Consult with EPA to learn implementation | 2026-02-04 09:00 | 2026-02-04 17:00 | 0.33333
Steam - Create implementation framework | 2026-02-05 09:00 | 2026-02-11 17:00 | 6.3333
Fuel Balance Benefit Quantification | 2026-01-30 09:00 | 2026-02-11 17:00 | 12.3333
Fuel - Establish benefit measurement methodology | 2026-01-30 09:00 | 2026-02-03 17:00 | 4.3333
Fuel - Consult with EPA to learn implementation | 2026-02-04 09:00 | 2026-02-04 17:00 | 0.33333
Fuel - Create implementation framework | 2026-02-05 09:00 | 2026-02-11 17:00 | 6.3333
Production Yield Benefit Quantification | 2026-01-30 09:00 | 2026-02-11 17:00 | 12.3333
Yield - Establish benefit measurement methodology | 2026-01-30 09:00 | 2026-02-03 17:00 | 4.3333
Yield - Consult with EPA to learn implementation | 2026-02-04 09:00 | 2026-02-04 17:00 | 0.33333
Yield - Create implementation framework | 2026-02-05 09:00 | 2026-02-11 17:00 | 6.3333
Develop Case Study & Review | 2026-02-12 09:00 | 2026-03-10 16:00 | 26.2917
Steam Network Case Study | 2026-02-12 09:00 | 2026-03-10 16:00 | 26.2917
Steam Case Study - Share with CS | 2026-02-12 09:00 | 2026-03-03 17:00 | 19.3333
Steam Case Study - Import | 2026-03-04 09:00 | 2026-03-05 17:00 | 1.3333
Steam Case Study - Check & Proofread | 2026-03-06 09:00 | 2026-03-10 16:00 | 4.2917
Fuel Balance Case Study | 2026-02-12 09:00 | 2026-03-10 16:00 | 26.2917
Fuel Case Study - Share content with CS | 2026-02-12 09:00 | 2026-03-03 17:00 | 19.3333
Fuel Case Study - Import | 2026-03-04 09:00 | 2026-03-05 17:00 | 1.3333
Fuel Case Study - Check & Proofread | 2026-03-06 09:00 | 2026-03-10 16:00 | 4.2917
Production Yield Case Study | 2026-02-12 09:00 | 2026-03-10 16:00 | 26.2917
Yield Case Study - Share content with CS | 2026-02-12 09:00 | 2026-03-03 17:00 | 19.3333
Yield Case Study - Import | 2026-03-04 09:00 | 2026-03-05 17:00 | 1.3333
Yield Case Study - Check & Proofread | 2026-03-06 09:00 | 2026-03-10 16:00 | 4.2917
Executive Review of IBA Results | 2026-03-11 08:00 | 2026-03-17 16:00 | 6.3333
Steam Network IBA Review | 2026-03-11 08:00 | 2026-03-17 16:00 | 6.3333
Steam - Exec approval of financial benefit | 2026-03-11 08:00 | 2026-03-17 16:00 | 6.3333
Fuel Balance IBA Review | 2026-03-11 08:00 | 2026-03-17 16:00 | 6.3333
Fuel - Exec approval of financial benefit | 2026-03-11 08:00 | 2026-03-17 16:00 | 6.3333
Production Yield IBA Review | 2026-03-11 08:00 | 2026-03-17 16:00 | 6.3333
Yield - Exec approval of financial benefit | 2026-03-11 08:00 | 2026-03-17 16:00 | 6.3333
Develop IBA Deck | 2026-03-18 08:00 | 2026-03-24 16:00 | 6.3333
Steam Network IBA Deck | 2026-03-18 08:00 | 2026-03-20 16:00 | 2.3333
Steam Deck - Develop design framework | 2026-03-18 08:00 | 2026-03-20 16:00 | 2.3333
Steam Deck - Develop storyboard | 2026-03-18 08:00 | 2026-03-20 16:00 | 2.3333
Fuel Balance IBA Deck | 2026-03-18 08:00 | 2026-03-20 16:00 | 2.3333
Fuel Deck - Develop design framework | 2026-03-18 08:00 | 2026-03-20 16:00 | 2.3333
Fuel Deck - Develop storyboard | 2026-03-18 08:00 | 2026-03-20 16:00 | 2.3333
Production Yield IBA Deck | 2026-03-18 08:00 | 2026-03-20 16:00 | 2.3333
Yield Deck - Develop design framework | 2026-03-18 08:00 | 2026-03-20 16:00 | 2.3333
Yield Deck - Develop storyboard | 2026-03-18 08:00 | 2026-03-20 16:00 | 2.3333
Series 1 - Complete IBA Deck | 2026-03-23 08:00 | 2026-03-23 16:00 | 0.33333
Series 1 - IBA Deck - Executive Review | 2026-03-24 08:00 | 2026-03-24 16:00 | 0.33333
Series 1 - POV Portal - Executive Review | 2026-03-18 08:00 | 2026-03-18 16:00 | 0.33333
Series 2 IBA Development | 2026-03-25 08:00 | 2026-06-24 16:00 | 91.3333
Data Qualification | 2026-03-25 08:00 | 2026-05-29 16:00 | 65.3333
Feedstock Utilization Data Qualification | 2026-03-25 08:00 | 2026-04-03 16:00 | 9.3333
Feedstock - Establish Data Connection | 2026-03-25 08:00 | 2026-03-25 16:00 | 0.33333
Feedstock - Validate Data | 2026-03-26 08:00 | 2026-03-30 16:00 | 4.3333
Feedstock - Check Data Availability | 2026-03-31 08:00 | 2026-04-02 16:00 | 2.3333
Feedstock - Mark Receipt of Each Data Source | 2026-04-03 08:00 | 2026-04-03 16:00 | 0.33333
Product Quality Data Qualification | 2026-05-26 08:00 | 2026-05-29 16:00 | 3.3333
Quality - Establish Data Connection | 2026-05-26 08:00 | 2026-05-26 16:00 | 0.33333
Quality - Validate Data | 2026-05-27 08:00 | 2026-05-27 16:00 | 0.33333
Quality - Check Data Availability | 2026-05-28 08:00 | 2026-05-28 16:00 | 0.33333
Quality - Mark Receipt of Each Data Source | 2026-05-29 08:00 | 2026-05-29 16:00 | 0.33333
Product Transition Data Qualification | 2026-05-26 08:00 | 2026-05-29 16:00 | 3.3333
Product Transition - Establish Data Connection | 2026-05-26 08:00 | 2026-05-26 16:00 | 0.33333
Product Transition - Validate Data | 2026-05-27 08:00 | 2026-05-27 16:00 | 0.33333
Product Transition - Check Data Availability | 2026-05-28 08:00 | 2026-05-28 16:00 | 0.33333
Product Transition - Mark Receipt of Each Data Source | 2026-05-29 08:00 | 2026-05-29 16:00 | 0.33333
Digital Twin, Mapping and Prediction | 2026-04-06 08:00 | 2026-06-16 16:00 | 71.3333
Feedstock Utilization Digital Twin | 2026-04-06 08:00 | 2026-04-20 16:00 | 14.3333
Feedstock - Determine relevant tags & target | 2026-04-06 08:00 | 2026-04-08 16:00 | 2.3333
Feedstock - DS KT session | 2026-04-09 08:00 | 2026-04-09 16:00 | 0.33333
Feedstock - Label tags for the models | 2026-04-09 08:00 | 2026-04-13 16:00 | 4.3333
Feedstock - Create Bounds & Changing Rates | 2026-04-14 08:00 | 2026-04-14 16:00 | 0.33333
Feedstock - Generate model | 2026-04-15 08:00 | 2026-04-15 16:00 | 0.33333
Feedstock - Ensure correct formatting and that data is uploaded to Maestro | 2026-04-16 08:00 | 2026-04-20 16:00 | 4.3333
Product Quality Digital Twin | 2026-06-01 08:00 | 2026-06-15 16:00 | 14.3333
Quality - Determine relevant tags & target | 2026-06-01 08:00 | 2026-06-03 16:00 | 2.3333
Quality - DS KT session | 2026-06-04 08:00 | 2026-06-04 16:00 | 0.33333
Quality - Label tags for the models | 2026-06-04 08:00 | 2026-06-08 16:00 | 4.3333
Quality - Create Bounds & Changing Rates | 2026-06-09 08:00 | 2026-06-09 16:00 | 0.33333
Quality - Generate model | 2026-06-10 08:00 | 2026-06-10 16:00 | 0.33333
Quality - Ensure correct formatting and that data is uploaded to Maestro | 2026-06-11 08:00 | 2026-06-15 16:00 | 4.3333
Product Transition Digital Twin | 2026-06-01 08:00 | 2026-06-15 16:00 | 14.3333
Product Transition - Determine relevant tags & target | 2026-06-01 08:00 | 2026-06-03 16:00 | 2.3333
Product Transition - DS KT session | 2026-06-04 08:00 | 2026-06-04 16:00 | 0.33333
Product Transition - Label tags for the models | 2026-06-04 08:00 | 2026-06-08 16:00 | 4.3333
Product Transition - Create Bounds & Changing Rates | 2026-06-09 08:00 | 2026-06-09 16:00 | 0.33333
Product Transition - Generate model | 2026-06-10 08:00 | 2026-06-10 16:00 | 0.33333
Product Transition - Ensure correct formatting and that data is uploaded to Maestro | 2026-06-11 08:00 | 2026-06-15 16:00 | 4.3333
Stack Series LSTM Models | 2026-06-16 08:00 | 2026-06-16 16:00 | 0.33333
Benefit Quantification | 2026-04-16 08:00 | 2026-06-15 16:00 | 60.3333
Feedstock Utilization Benefit Quantification | 2026-04-16 08:00 | 2026-04-28 16:00 | 12.3333
Feedstock - Establish benefit measurement methodology | 2026-04-16 08:00 | 2026-04-20 16:00 | 4.3333
Feedstock - Consult with EPA to learn implementation | 2026-04-21 08:00 | 2026-04-21 16:00 | 0.33333
Feedstock - Create implementation framework | 2026-04-22 08:00 | 2026-04-28 16:00 | 6.3333
Product Quality Benefit Quantification | 2026-06-11 08:00 | 2026-06-15 16:00 | 4.3333
Quality - Establish benefit measurement methodology | 2026-06-11 08:00 | 2026-06-11 16:00 | 0.33333
Quality - Consult with EPA to learn implementation | 2026-06-12 08:00 | 2026-06-12 16:00 | 0.33333
Quality - Create implementation framework | 2026-06-15 08:00 | 2026-06-15 16:00 | 0.33333
Product Transition Benefit Quantification | 2026-06-11 08:00 | 2026-06-15 16:00 | 4.3333
Product Transition - Establish benefit measurement methodology | 2026-06-11 08:00 | 2026-06-11 16:00 | 0.33333
Product Transition - Consult with EPA to learn implementation | 2026-06-12 08:00 | 2026-06-12 16:00 | 0.33333
Product Transition - Create implementation framework | 2026-06-15 08:00 | 2026-06-15 16:00 | 0.33333
Develop Case Study & Review | 2026-04-29 08:00 | 2026-06-18 16:00 | 50.3333
Feedstock Utilization Case Study | 2026-04-29 08:00 | 2026-05-25 16:00 | 26.3333
Feedstock Case Study - Share with CS | 2026-04-29 08:00 | 2026-05-18 16:00 | 19.3333
Feedstock Case Study - Import | 2026-05-19 08:00 | 2026-05-20 16:00 | 1.3333
Feedstock Case Study - Check & Proofread | 2026-05-21 08:00 | 2026-05-25 16:00 | 4.3333
Product Quality Case Study | 2026-06-16 08:00 | 2026-06-18 16:00 | 2.3333
Quality Case Study - Share content with CS | 2026-06-16 08:00 | 2026-06-16 16:00 | 0.33333
Quality Case Study - Import | 2026-06-17 08:00 | 2026-06-17 16:00 | 0.33333
Quality Case Study - Check & Proofread | 2026-06-18 08:00 | 2026-06-18 16:00 | 0.33333
Product Transition Case Study | 2026-06-16 08:00 | 2026-06-18 16:00 | 2.3333
Product Transition Case Study - Share content with CS | 2026-06-16 08:00 | 2026-06-16 16:00 | 0.33333
Product Transition Case Study - Import | 2026-06-17 08:00 | 2026-06-17 16:00 | 0.33333
Product Transition Case Study - Check & Proofread | 2026-06-18 08:00 | 2026-06-18 16:00 | 0.33333
Executive Review of IBA Results | 2026-05-26 08:00 | 2026-06-19 16:00 | 24.3333
Feedstock Utilization IBA Review | 2026-05-26 08:00 | 2026-06-01 16:00 | 6.3333
Feedstock - Exec approval of financial benefit | 2026-05-26 08:00 | 2026-06-01 16:00 | 6.3333
Product Quality IBA Review | 2026-06-19 08:00 | 2026-06-19 16:00 | 0.33333
Quality - Exec approval of financial benefit | 2026-06-19 08:00 | 2026-06-19 16:00 | 0.33333
Product Transition IBA Review | 2026-06-19 08:00 | 2026-06-19 16:00 | 0.33333
Product Transition - Exec approval of financial benefit | 2026-06-19 08:00 | 2026-06-19 16:00 | 0.33333
Develop IBA Deck | 2026-06-02 08:00 | 2026-06-24 16:00 | 22.3333
Feedstock Utilization IBA Deck | 2026-06-02 08:00 | 2026-06-04 16:00 | 2.3333
Feedstock - Develop design framework | 2026-06-02 08:00 | 2026-06-04 16:00 | 2.3333
Feedstock - Develop storyboard | 2026-06-02 08:00 | 2026-06-04 16:00 | 2.3333
Product Quality IBA Deck | 2026-06-22 08:00 | 2026-06-22 16:00 | 0.33333
Quality - Develop design framework | 2026-06-22 08:00 | 2026-06-22 16:00 | 0.33333
Quality - Develop storyboard | 2026-06-22 08:00 | 2026-06-22 16:00 | 0.33333
Product Transition IBA Deck | 2026-06-22 08:00 | 2026-06-22 16:00 | 0.33333
Product Transition Deck - Develop design framework | 2026-06-22 08:00 | 2026-06-22 16:00 | 0.33333
Product Transition Deck - Develop storyboard | 2026-06-22 08:00 | 2026-06-22 16:00 | 0.33333
Series 2 - Complete IBA Deck | 2026-06-23 08:00 | 2026-06-23 16:00 | 0.33333
Series 2 - IBA Deck - Executive Review | 2026-06-24 08:00 | 2026-06-24 16:00 | 0.33333
Series 2 - POV Portal - Executive Review | 2026-06-22 08:00 | 2026-06-22 16:00 | 0.33333
Series 3 IBA Development | 2026-06-25 08:00 | 2026-09-24 16:00 | 91.3333
Data Qualification | 2026-06-25 08:00 | 2026-08-31 16:00 | 67.3333
Planning & Scheduling Data Qualification | 2026-06-25 08:00 | 2026-07-06 16:00 | 11.3333
P&S - Establish Data Connection | 2026-06-25 08:00 | 2026-06-25 16:00 | 0.33333
P&S - Validate Data | 2026-06-26 08:00 | 2026-06-30 16:00 | 4.3333
P&S - Check Data Availability | 2026-07-01 08:00 | 2026-07-03 16:00 | 2.3333
P&S - Mark Receipt of Each Data Source | 2026-07-06 08:00 | 2026-07-06 16:00 | 0.33333
Asset Health & Maintenance Data Qualification | 2026-08-26 08:00 | 2026-08-31 16:00 | 5.3333
Maintenance - Establish Data Connection | 2026-08-26 08:00 | 2026-08-26 16:00 | 0.33333
Maintenance - Validate Data | 2026-08-27 08:00 | 2026-08-27 16:00 | 0.33333
Maintenance - Check Data Availability | 2026-08-28 08:00 | 2026-08-28 16:00 | 0.33333
Maintenance - Mark Receipt of Each Data Source | 2026-08-31 08:00 | 2026-08-31 16:00 | 0.33333
Plant Resource Efficiency Data Qualification | 2026-08-26 08:00 | 2026-08-31 16:00 | 5.3333
RE - Establish Data Connection | 2026-08-26 08:00 | 2026-08-26 16:00 | 0.33333
RE - Validate Data | 2026-08-27 08:00 | 2026-08-27 16:00 | 0.33333
RE - Check Data Availability | 2026-08-28 08:00 | 2026-08-28 16:00 | 0.33333
RE - Mark Receipt of Each Data Source | 2026-08-31 08:00 | 2026-08-31 16:00 | 0.33333
Digital Twin, Mapping and Prediction | 2026-07-07 08:00 | 2026-09-16 16:00 | 71.3333
Planning & Scheduling Digital Twin | 2026-07-07 08:00 | 2026-07-21 16:00 | 14.3333
P&S - Determine relevant tags & target | 2026-07-07 08:00 | 2026-07-09 16:00 | 2.3333
P&S - DS KT session | 2026-07-10 08:00 | 2026-07-10 16:00 | 0.33333
P&S - Label tags for the models | 2026-07-10 08:00 | 2026-07-14 16:00 | 4.3333
P&S - Create Bounds & Changing Rates | 2026-07-15 08:00 | 2026-07-15 16:00 | 0.33333
P&S - Generate model | 2026-07-16 08:00 | 2026-07-16 16:00 | 0.33333
P&S - Ensure correct formatting and that data is uploaded to Maestro | 2026-07-17 08:00 | 2026-07-21 16:00 | 4.3333
Asset Health & Maintenance Digital Twin | 2026-09-01 08:00 | 2026-09-15 16:00 | 14.3333
Maintenance - Determine relevant tags & target | 2026-09-01 08:00 | 2026-09-03 16:00 | 2.3333
Maintenance - DS KT session | 2026-09-04 08:00 | 2026-09-04 16:00 | 0.33333
Maintenance - Label tags for the models | 2026-09-04 08:00 | 2026-09-08 16:00 | 4.3333
Maintenance - Create Bounds & Changing Rates | 2026-09-09 08:00 | 2026-09-09 16:00 | 0.33333
Maintenance - Generate model | 2026-09-10 08:00 | 2026-09-10 16:00 | 0.33333
Maintenance - Ensure correct formatting and that data is uploaded to Maestro | 2026-09-11 08:00 | 2026-09-15 16:00 | 4.3333
Plant Resource Efficiency Digital Twin | 2026-09-01 08:00 | 2026-09-15 16:00 | 14.3333
RE - Determine relevant tags & target | 2026-09-01 08:00 | 2026-09-03 16:00 | 2.3333
RE - DS KT session | 2026-09-04 08:00 | 2026-09-04 16:00 | 0.33333
RE - Label tags for the models | 2026-09-04 08:00 | 2026-09-08 16:00 | 4.3333
RE - Create Bounds & Changing Rates | 2026-09-09 08:00 | 2026-09-09 16:00 | 0.33333
RE - Generate model | 2026-09-10 08:00 | 2026-09-10 16:00 | 0.33333
RE - Ensure correct formatting and that data is uploaded to Maestro | 2026-09-11 08:00 | 2026-09-15 16:00 | 4.3333
Stack Series LSTM Models | 2026-09-16 08:00 | 2026-09-16 16:00 | 0.33333
Benefit Quantification | 2026-07-17 08:00 | 2026-09-15 16:00 | 60.3333
Planning & Scheduling Benefit Quantification | 2026-07-17 08:00 | 2026-07-29 16:00 | 12.3333
P&S - Establish benefit measurement methodology | 2026-07-17 08:00 | 2026-07-21 16:00 | 4.3333
P&S - Consult with EPA to learn implementation | 2026-07-22 08:00 | 2026-07-22 16:00 | 0.33333
P&S - Create implementation framework | 2026-07-23 08:00 | 2026-07-29 16:00 | 6.3333
Asset Health & Maintenance Benefit Quantification | 2026-09-11 08:00 | 2026-09-15 16:00 | 4.3333
Maintenance - Establish benefit measurement methodology | 2026-09-11 08:00 | 2026-09-11 16:00 | 0.33333
Maintenance - Consult with EPA to learn implementation | 2026-09-14 08:00 | 2026-09-14 16:00 | 0.33333
Maintenance - Create implementation framework | 2026-09-15 08:00 | 2026-09-15 16:00 | 0.33333
Plant Resource Efficiency Benefit Quantification | 2026-09-11 08:00 | 2026-09-15 16:00 | 4.3333
RE - Establish benefit measurement methodology | 2026-09-11 08:00 | 2026-09-11 16:00 | 0.33333
RE - Consult with EPA to learn implementation | 2026-09-14 08:00 | 2026-09-14 16:00 | 0.33333
RE - Create implementation framework | 2026-09-15 08:00 | 2026-09-15 16:00 | 0.33333
Develop Case Study & Review | 2026-07-30 08:00 | 2026-09-18 16:00 | 50.3333
Planning & Scheduling Case Study | 2026-07-30 08:00 | 2026-08-25 16:00 | 26.3333
P&S Case Study - Share with CS | 2026-07-30 08:00 | 2026-08-18 16:00 | 19.3333
P&S Case Study - Import | 2026-08-19 08:00 | 2026-08-20 16:00 | 1.3333
P&S Case Study - Check & Proofread | 2026-08-21 08:00 | 2026-08-25 16:00 | 4.3333
Asset Health & Maintenance Case Study | 2026-09-16 08:00 | 2026-09-18 16:00 | 2.3333
Maintenance Case Study - Share content with CS | 2026-09-16 08:00 | 2026-09-16 16:00 | 0.33333
Maintenance Case Study - Import | 2026-09-17 08:00 | 2026-09-17 16:00 | 0.33333
Maintenance Case Study - Check & Proofread | 2026-09-18 08:00 | 2026-09-18 16:00 | 0.33333
Plant Resource Efficiency Case Study | 2026-09-16 08:00 | 2026-09-18 16:00 | 2.3333
RE Case Study - Share content with CS | 2026-09-16 08:00 | 2026-09-16 16:00 | 0.33333
RE Case Study - Import | 2026-09-17 08:00 | 2026-09-17 16:00 | 0.33333
RE Case Study - Check & Proofread | 2026-09-18 08:00 | 2026-09-18 16:00 | 0.33333
Executive Review of IBA Results | 2026-08-26 08:00 | 2026-09-21 16:00 | 26.3333
Planning & Scheduling IBA Review | 2026-08-26 08:00 | 2026-09-01 16:00 | 6.3333
P&S - Exec approval of financial benefit | 2026-08-26 08:00 | 2026-09-01 16:00 | 6.3333
Asset Health & Maintenance IBA Review | 2026-09-21 08:00 | 2026-09-21 16:00 | 0.33333
Maintenance - Exec approval of financial benefit | 2026-09-21 08:00 | 2026-09-21 16:00 | 0.33333
Plant Resource Efficiency IBA Review | 2026-09-21 08:00 | 2026-09-21 16:00 | 0.33333
RE - Exec approval of financial benefit | 2026-09-21 08:00 | 2026-09-21 16:00 | 0.33333
Develop IBA Deck | 2026-09-02 08:00 | 2026-09-24 16:00 | 22.3333
Planning & Scheduling IBA Deck | 2026-09-02 08:00 | 2026-09-04 16:00 | 2.3333
P&S - Develop design framework | 2026-09-02 08:00 | 2026-09-04 16:00 | 2.3333
P&S - Develop storyboard | 2026-09-02 08:00 | 2026-09-04 16:00 | 2.3333
Asset Health & Maintenance IBA Deck | 2026-09-22 08:00 | 2026-09-22 16:00 | 0.33333
Maintenance - Develop design framework | 2026-09-22 08:00 | 2026-09-22 16:00 | 0.33333
Maintenance - Develop storyboard | 2026-09-22 08:00 | 2026-09-22 16:00 | 0.33333
Plant Resource Efficiency IBA Deck | 2026-09-22 08:00 | 2026-09-22 16:00 | 0.33333
RE Deck - Develop design framework | 2026-09-22 08:00 | 2026-09-22 16:00 | 0.33333
RE Deck - Develop storyboard | 2026-09-22 08:00 | 2026-09-22 16:00 | 0.33333
Series 3 - Complete IBA Deck | 2026-09-23 08:00 | 2026-09-23 16:00 | 0.33333
Series 3 - IBA Deck - Executive Review | 2026-09-24 08:00 | 2026-09-24 16:00 | 0.33333
Series 3 - POV Portal - Executive Review | 2026-09-22 08:00 | 2026-09-22 16:00 | 0.33333
Go Live Deployment | 2026-09-25 08:00 | 2026-12-31 17:00 | 97.375
Live Data Integration | 2026-09-25 08:00 | 2026-10-09 16:00 | 14.3333
Finalize list of data sources | 2026-09-25 08:00 | 2026-09-28 16:00 | 3.3333
Find integration solution | 2026-09-29 08:00 | 2026-09-29 16:00 | 0.33333
Confirm IT architecture | 2026-09-25 08:00 | 2026-09-25 16:00 | 0.33333
Finalize IT Architecture | 2026-09-28 08:00 | 2026-10-09 16:00 | 11.3333
Deploy Gateway Server | 2026-09-25 08:00 | 2026-09-25 16:00 | 0.33333
Outbound Connection to Maestro | 2026-09-28 08:00 | 2026-09-28 16:00 | 0.33333
Client prepare environment |  |  | #VALUE!
Make Live Connection | 2026-09-28 08:00 | 2026-09-28 16:00 | 0.33333
Validate Live Data Connection | 2026-09-25 08:00 | 2026-09-25 16:00 | 0.33333
Test VPN Connection |  |  | #VALUE!
CM to M or Push Data to Maestro | 2026-09-25 08:00 | 2026-10-08 16:00 | 13.3333
Configure Maestro Performance Center | 2026-09-25 08:00 | 2026-11-11 17:00 | 47.375
Generate KPI list | 2026-09-25 08:00 | 2026-10-05 16:00 | 10.3333
Build KPI formulas | 2026-10-06 08:00 | 2026-10-14 16:00 | 8.3333
KT w/DS for KPIs to be produced | 2026-10-15 08:00 | 2026-10-15 16:00 | 0.33333
Create initial KPI output values | 2026-10-16 08:00 | 2026-10-20 16:00 | 4.3333
Validate KPI output values | 2026-10-21 08:00 | 2026-10-23 16:00 | 2.3333
Provide 'when not to display' rule | 2026-10-26 08:00 | 2026-10-26 16:00 | 0.33333
Modify KPI formulas where possible | 2026-10-26 08:00 | 2026-10-30 16:00 | 4.3333
Build out KPI list in maestro | 2026-11-02 09:00 | 2026-11-10 17:00 | 8.3333
Executive review of Performance Center | 2026-11-11 09:00 | 2026-11-11 17:00 | 0.33333
Live Test Model Transition | 2026-09-29 08:00 | 2026-12-25 17:00 | 87.375
Create fault tolerance mechanisms | 2026-11-12 09:00 | 2026-11-16 17:00 | 4.3333
Test fault tolerance mechanism | 2026-11-17 09:00 | 2026-11-30 17:00 | 13.3333
Update bound & changing rates | 2026-11-11 09:00 | 2026-11-12 17:00 | 1.3333
Confirm manual data sharing methods and locations | 2026-09-29 08:00 | 2026-10-01 16:00 | 2.3333
Confirm receipt of data | 2026-09-29 08:00 | 2026-10-02 16:00 | 3.3333
Publish Model | 2026-11-13 09:00 | 2026-12-02 17:00 | 19.3333
Create test period for directive issuance | 2026-12-03 09:00 | 2026-12-03 17:00 | 0.33333
Update directive issuance | 2026-12-04 09:00 | 2026-12-10 17:00 | 6.3333
Update Models | 2026-12-11 09:00 | 2026-12-24 17:00 | 13.3333
Finalize and Deploy Live Test Models | 2026-12-25 09:00 | 2026-12-25 17:00 | 0.33333
Go Live Governance | 2026-12-28 09:00 | 2026-12-31 17:00 | 3.3333
Set client weekly meeting time | 2026-12-28 09:00 | 2026-12-28 17:00 | 0.33333
Hold first weekly client meeting | 2026-12-29 09:00 | 2026-12-29 17:00 | 0.33333
Publish Live Test Status Update | 2026-12-29 09:00 | 2026-12-29 17:00 | 0.33333
Determine what access LYB employees will have | 2026-12-28 09:00 | 2026-12-28 17:00 | 0.33333
Grant limited access | 2026-12-29 09:00 | 2026-12-29 17:00 | 0.33333
Meet with LYB to explain functionality | 2026-12-30 09:00 | 2026-12-30 17:00 | 0.33333
Commence directive implementation | 2026-12-31 09:00 | 2026-12-31 17:00 | 0.33333
Implementation Control | 2026-09-25 08:00 | 2026-11-05 17:00 | 41.375
Series 1 | 2026-09-25 08:00 | 2026-10-08 16:00 | 13.3333
Expedite Maestro control | 2026-09-25 08:00 | 2026-09-25 16:00 | 0.33333
Develop implementation detection | 2026-09-25 08:00 | 2026-10-01 16:00 | 6.3333
Create known route to implementation | 2026-09-25 08:00 | 2026-09-25 16:00 | 0.33333
Create implementation report outline | 2026-10-02 08:00 | 2026-10-08 16:00 | 6.3333
Revisit Automated Control | 2026-09-25 08:00 | 2026-09-25 16:00 | 0.33333
Series 2 | 2026-10-09 08:00 | 2026-10-22 16:00 | 13.3333
Expedite Maestro control | 2026-10-09 08:00 | 2026-10-09 16:00 | 0.33333
Develop implementation detection | 2026-10-09 08:00 | 2026-10-15 16:00 | 6.3333
Create known route to implementation | 2026-10-09 08:00 | 2026-10-09 16:00 | 0.33333
Create implementation report outline | 2026-10-16 08:00 | 2026-10-22 16:00 | 6.3333
Revisit Automated Control | 2026-10-09 08:00 | 2026-10-09 16:00 | 0.33333
Series 3 | 2026-10-23 08:00 | 2026-11-05 17:00 | 13.375
Expedite Maestro control | 2026-10-23 08:00 | 2026-10-23 16:00 | 0.33333
Develop implementation detection | 2026-10-23 08:00 | 2026-10-29 16:00 | 6.3333
Create known route to implementation | 2026-10-23 08:00 | 2026-10-23 16:00 | 0.33333
Create implementation report outline | 2026-10-30 08:00 | 2026-11-05 17:00 | 6.375
Revisit Automated Control | 2026-10-23 08:00 | 2026-10-23 16:00 | 0.33333
Review first implementation report | 2026-10-09 08:00 | 2026-10-09 16:00 | 0.33333
Ongoing Delivery | 2027-01-01 09:00 | 2027-02-05 17:00 | 35.3333
Client Workstream Owner Introductions | 2027-01-01 09:00 | 2027-01-20 17:00 | 19.3333
Client Services | 2027-01-01 09:00 | 2027-01-20 17:00 | 19.3333
Introductions to client owners for each workstream | 2027-01-01 09:00 | 2027-01-20 17:00 | 19.3333
Internal Weekly Call | 2027-01-21 09:00 | 2027-01-21 17:00 | 0.33333
Set Internal Weekly Call | 2027-01-21 09:00 | 2027-01-21 17:00 | 0.33333
Ensure correct audience Internal Weekly Call | 2027-01-21 09:00 | 2027-01-21 17:00 | 0.33333
Weekly Client Call | 2027-01-22 09:00 | 2027-01-22 17:00 | 0.33333
Set Weekly Client Call | 2027-01-22 09:00 | 2027-01-22 17:00 | 0.33333
Ensure correct audience Weekly Client Call | 2027-01-22 09:00 | 2027-01-22 17:00 | 0.33333
Reporting | 2027-01-25 09:00 | 2027-02-05 17:00 | 11.3333
Publish Executive Report every month | 2027-01-25 09:00 | 2027-02-05 17:00 | 11.3333
Issue Weekly Live Test Updates | 2027-01-25 09:00 | 2027-01-27 17:00 | 2.3333

## Project goals
Name | Priority | Status | Start date | End date | Description | Connected tasks
Pre-Kick Off Plan Activities | Medium | Not started |  |  |  | 23-DRT - 1st Draft, 26-DRT - Finalized, 10-Determine Use Cases, 12-P&L - 1st Draft, 15-P&L - Finalized, 17-SOW - 1st Draft, 28-EP - 1st Draft, 31-EP - Final Draft, 37-Liaise with Legal to Complete Drafts, 34-Outline rough case studies, 40-Prepare IT Architecture Diagram
Complete POV | Medium | Not started |  |  |  | 86-Complete historical data collection, 366-Series 3 - IBA Deck - Executive Review, 280-Series 2 - IBA Deck - Executive Review, 194-Series 1 - IBA Deck - Executive Review, 195-Series 1 - POV Portal - Executive Review, 367-Series 3 - POV Portal - Executive Review, 281-Series 2 - POV Portal - Executive Review, 50-Hold External Kick-off Meeting, 109-Complete development of POV portal, 178-Steam - Exec approval of financial benefit, 264-Feedstock - Exec approval of financial benefit, 180-Fuel - Exec approval of financial benefit, 266-Quality - Exec approval of financial benefit, 182-Yield - Exec approval of financial benefit, 354-RE - Exec approval of financial benefit, 268-Product Transition - Exec approval of financial benefit, 352-Maintenance - Exec approval of financial benefit, 350-P&S - Exec approval of financial benefit
Go Live Deployment | Medium | Not started |  |  |  | 390-Executive review of Performance Center, 401-Finalize and Deploy Live Test Models, 404-Hold first weekly client meeting, 409-Commence directive implementation, 429-Review first implementation report, 374-Deploy Gateway Server, 378-Validate Live Data Connection